## Sheet1
2019-10-09 | WEDNESDAY | Bring up the gun with the old cathode | Injector setup, Phase MLC | Measure the cathode QE – make sure that it survived the power outage
2019-10-10 | THURSDAY | 6 MeV beam to the diagnostic line. |  | Diagnostic line measurements. BPM charge calibration with faraday cup, emittance/phase measurements to make sure we are close to where we need to be.
2019-10-11 | FRIDAY | Measure the beam properties
2019-10-12 | SATURDAY
2019-10-13 | SUNDAY
2019-10-14 | Monday | 6 MeV beam to the beam dump
2019-10-15 | Tuesday | 42 MeV beam to the S1 beam line
2019-10-16 | Wednesday | 42 MeV beam to the S1 beam line
2019-10-17 | Thursday | 42 MeV beam through the S1 and FFA
2019-10-18 | Friday | 42 MeV beam through the R1 beam line
2019-10-19 | Saturday | 42 MeV beam up to the MLC
2019-10-20 | Sunday
2019-10-21 | Monday | Commission second deceleration pass into S2 and R2
2019-10-22 | Tuesday | Commission third deceleration pass into S1 and R1
2019-10-23 | Wednesday | Commission fourth deceleration pass into dump line
2019-10-24 | Thursday | Commissioning of the S2 beam line
2019-10-25 | Friday | Commissioning of the S2 beam line
2019-10-26 | Saturday | Ongoing commissioing and tuning, increase intensity
2019-10-27 | Sunday | Ongoing commissioing and tuning, increase intensity
2019-10-28 | Monday | Orbit corrections of both 42 and 78 MeV beams in FFA’s
2019-10-29 | Tuesday | The S2, FFA, and R2 beam line commissioning with two beams in the FFA two beam
2019-10-30 | Wednesday | The S2, FFA, and R2 beam line commissioning with two beams in the FFA two beam
2019-10-31 | Thursday | The S2, FFA, and R2 beam line commissioning with two beams in the FFA two beam
2019-11-01 | Friday | S3 beam line commissioning – 114 MeV beam scraped before FFA
2019-11-02 | Saturday
2019-11-03 | Sunday
2019-11-04 | Monday | Three beams through the FFA 42 MeV, 78 MeV, and 114 MeV
2019-11-05 | Tuesday | Three beams through the FFA 42 MeV, 78 MeV, and 114 MeV
2019-11-06 | Wednesday | Three beams through the FFA 42 MeV, 78 MeV, and 114 MeV
2019-11-07 | Thursday | R3 114 MeV beam line commissioning
2019-11-08 | Friday | R3 114 MeV beam line commissioning
2019-11-09 | Saturday
2019-11-10 | Sunday
2019-11-11 | Monday | S4 150 MeV beam line commissioning
2019-11-12 | Tuesday | S4 150 MeV beam line commissioning
2019-11-13 | Wednesday | Four beams going through the FFA beam line
2019-11-14 | Thursday | Time of flight measurements and adjustments
2019-11-15 | Friday | R4 beam line commissioning
2019-11-16 | Saturday
2019-11-17 | Sunday
2019-11-18 | Monday | ACCELERATION WITH ENERGY RECOVERY
2019-11-19 | Tuesday | ACCELERATION WITH ENERGY RECOVERY
2019-11-20 | Wednesday | ACCELERATION WITH ENERGY RECOVERY
2019-11-21 | Thursday | ACCELERATION WITH ENERGY RECOVERY
2019-11-22 | Friday | ACCELERATION WITH ENERGY RECOVERY
2019-11-23 | Saturday
2019-11-24 | Sunday
2019-11-25 | Monday | ACCELERATION WITH ENERGY RECOVERY
2019-11-26 | Tuesday | ACCELERATION WITH ENERGY RECOVERY
2019-11-27 | Wednesday | ACCELERATION WITH ENERGY RECOVERY
2019-11-28 | Thursday | ACCELERATION WITH ENERGY RECOVERY
2019-11-29 | Friday | ACCELERATION WITH ENERGY RECOVERY
2019-11-30 | Saturday
2019-12-01 | Sunday
2019-12-02 | Monday | ACCELERATION WITH ENERGY RECOVERY
2019-12-03 | Tuesday | ACCELERATION WITH ENERGY RECOVERY
2019-12-04 | Wednesday | ACCELERATION WITH ENERGY RECOVERY
2019-12-05 | Thursday | ACCELERATION WITH ENERGY RECOVERY
2019-12-06 | Friday | ACCELERATION WITH ENERGY RECOVERY
2019-12-07 | Saturday
2019-12-08 | Sunday
2019-12-09 | Monday | ACCELERATION WITH ENERGY RECOVERY
2019-12-10 | Tuesday | ACCELERATION WITH ENERGY RECOVERY
2019-12-11 | Wednesday | ACCELERATION WITH ENERGY RECOVERY
2019-12-12 | Thursday | ACCELERATION WITH ENERGY RECOVERY
2019-12-13 | Friday | ACCELERATION WITH ENERGY RECOVERY
2019-12-14 | Saturday
2019-12-15 | Sunday
2019-12-16 | Monday | ACCELERATION WITH ENERGY RECOVERY
2019-12-17 | Tuesday | ACCELERATION WITH ENERGY RECOVERY
2019-12-18 | Wednesday | ACCELERATION WITH ENERGY RECOVERY
2019-12-19 | Thursday | ACCELERATION WITH ENERGY RECOVERY
2019-12-20 | Friday | ACCELERATION WITH ENERGY RECOVERY
2019-12-21 | Saturday
2019-12-22 | Sunday
2019-12-23 | Monday | ACCELERATION WITH ENERGY RECOVERY
2019-12-24 | Tuesday
2019-12-25 | Wednesday
2019-12-26 | Thursday
2019-12-27 | Friday
2019-12-28 | Saturday
2019-12-29 | Sunday