## GDE
[8 empty] | -------------- |  | Draft budget request |  |  |  | --------------
[8 empty] | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | NSF FY07
[8 empty] | Labor | Labor | M&S | M&S | Total | Total
WBS | Description |  |  |  | Lab/Univ | WP leader | FTE | Direct | Indirect | Direct | Indirect | Indirect
1 | Program direction and administration | [5 empty] | 11.85 | 1481.5 | 508.0925 | 1219 | 186.9855 | 695.078 | 4008.578 | 326
| 1.1 | Program management-SLAC |  |  | SLAC | Raubenheimer | 4.5 | 607.5 | 224.775 | 550 | 82.5 | 307.275 | 1464.775
| 1.2 | Program management-Fermilab |  |  | FNAL | Kephart | 6 | 690 | 209.415 | 601 | 96.4605 | 305.8755 | 1596.8755
| 1.3 | Program management-LBNL |  |  |  |  | 0.35 | 69 | 39 | 18 | 0 | 39 | 126
|  | 1.3.1 | Coordination of GDE-wide Damping Ring R&D |  | LBNL | Wolski | 0 | 0 | 0 |  |  | 0 | 0
|  | 1.3.2 | Coordination of Accelerator Effort at LBNL |  | LBNL | Wolski | 0.35 | 69 | 39 | 18 |  | 39 | 126
| 1.4 | ILC public relations |  |  | FNAL | Jackson | 1 | 115 | 34.9025 | 50 | 8.025 | 42.9275 | 207.9275
| 1.5 | ILC school |  |  | FNAL | Chou | [6 empty] | 0 |  | 0
| 1.6 | GDE Director travel |  |  | UNIV | Barish/Caltech | [6 empty] | 140
| 1.7 | GDE Common fund |  |  | FNAL | Barish | [6 empty] | 473
| 1.8 | Americas Regional Director |  |  | UNIV | Dugan/Cornell | [7 empty] | 326
| 1.9 | Collaboration and outreach |  |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
2 | Accelerator design, including TDR | [5 empty] | 45.6 | 6470.75 | 2326.9499 | 1169.2 | 163.415 | 2490.1649 | 10130.1149 | 0
| 2.1 | Management |  |  |  |  | 6.8 | 808 | 256.8988 | 250 | 40.125 | 297.0238 | 1355.0238 | 0
|  | 2.1.1 | Accelerator design management |  | SLAC | Phinney | 1.3 | 175.5 | 64.935 |  | 0 | 64.935 | 240.435
|  | 2.1.2 | Development of the reference design report |  | FNAL | Mishra | 5.5 | 632.5 | 191.9638 | 250 | 40.125 | 232.0888 | 1114.5887
| 2.2 | Global systems |  |  |  |  | 4.5 | 607.5 | 224.775 | 100 | 15 | 239.775 | 947.275 | 0
|  | 2.2.1 | Global systems design |  | SLAC | Himel | 1.5 | 202.5 | 74.925 |  | 0 | 74.925 | 277.425
|  | 2.2.2 | Control systems design |  | SLAC | Larsen | 1.5 | 202.5 | 74.925 |  | 0 | 74.925 | 277.425
|  | 2.2.3 | Installation |  | SLAC | Asiri | 1.5 | 202.5 | 74.925 | 100 | 15 | 89.925 | 392.425
| 2.3 | Electron sources |  |  |  |  | 1.5 | 202.5 | 74.925 | 0 | 0 | 74.925 | 277.425 | 0
|  | 2.3.1 | Electron source design |  | SLAC | Brachmann | 1.5 | 202.5 | 74.925 | 0 | 0 | 74.925 | 277.425
| 2.4 | Positron sources |  |  |  |  | 4.5 | 637.5 | 124.875 | 42 | 0 | 124.875 | 804.375 | 0
|  | 2.4.1 | Positron source design |  | SLAC | Sheppard | 2.5 | 337.5 | 124.875 |  | 0 | 124.875 | 462.375
|  | 2.4.2 | End-to-end simulation of positron source-und to DR |  | ANL | Gai | 2 | 300 | 0 | 42 |  | 0 | 342
| 2.5 | Damping rings |  |  |  |  | 11.9 | 2101.25 | 881.5031 | 136.2 | 8.225 | 889.5281 | 3126.9781 | 0
|  | 2.5.1 | Damping ring design |  | SLAC | Cai | 2.5 | 337.5 | 124.875 |  | 0 | 124.875 | 462.375
|  | 2.5.2 | Damping ring accelerator physics |  | FNAL | Spentzouris | 1.25 | 143.75 | 43.6281 | 50 | 8.025 | 51.6531 | 245.4031
|  | 2.5.3 | Damping Ring Injection & Extraction Beamline Design & Characterization |  | LBNL | Reichel | 0.5 | 98 | 55 | 3.4 | 0.2 | 55 | 156.4
|  | 2.5.4 | Damping Ring Beam Dynamics: Dynamic Aperture |  | LBNL | Reichel | 0.8 | 157 | 87 | 3.4 |  | 87 | 247.4
|  | 2.5.5 | Damping Ring Beam Dynamics: Collective Effects |  | LBNL | Venturini | 2 | 371 | 205 | 9 |  | 205 | 585
|  | 2.5.6 | Damping ring design and optimization |  | ANL | Xiao | 1.4 | 340 |  | 40 |  | 0 | 380
|  | 2.5.7 | Damping ring vacuum designs |  | LBNL |  | 0.75 | 147 | 82 | 5 |  | 82 | 234
|  | 2.5.8 | Damping ring mech systems design and integration |  | LBNL |  | 0.5 | 98 | 55 | 3.4 |  | 55 | 156.4
|  | 2.5.9 | Multibunch impedance |  | LBNL |  | 0.5 | 76 | 43 | 6 |  | 43 | 125
|  | 2.5.10 | Development of the transverse broadbanc multi-bunch FB systems |  | LBNL |  | 0.45 | 88 | 50 | 11 |  | 50 | 149
|  | 2.5.11 | Damping ring low emittance tuning |  | LBNL |  | 0.75 | 147 | 82 | 5 |  | 82 | 234
|  | 2.5.12 | Characterize the effects of inj/ext transients |  | LBNL |  | 0.5 | 98 | 54 |  |  | 54 | 152
| 2.6 | Ring to Main Linac |  |  |  |  | 1.2 | 162 | 59.94 | 0 | 0 | 59.94 | 221.94 | 0
|  | 2.6.1 | RTML design |  | SLAC | Tenenbaum | 1.2 | 162 | 59.94 |  | 0 | 59.94 | 221.94
| 2.7 | Main Linacs: Optics, beam dynamics, instrumentation |  |  |  |  | 7.6 | 934 | 310.4015 | 145 | 23.2725 | 333.674 | 1412.674 | 0
|  | 2.7.1 | Linac beamline design |  | SLAC | Tenenbaum | 1 | 135 | 49.95 |  | 0 | 49.95 | 184.95
|  | 2.7.2 | Wakefleids |  | SLAC | Bane | 2 | 270 | 99.9 |  | 0 | 99.9 | 369.9
|  | 2.7.3 | Main linac accelerator physics |  | FNAL | Solyak | 4.1 | 471.5 | 143.1002 | 95 | 15.2475 | 158.3477 | 724.8478
|  | 2.7.4 | Alignment and vibration |  | FNAL | Volk | 0.5 | 57.5 | 17.4513 | 50 | 8.025 | 25.4763 | 132.9762
| 2.8 | Main Linacs: RF systems
| 2.9 | Main Linacs: Cavities and Cryomodules
| 2.1 | Beam delivery system |  |  |  |  | 6 | 814 | 322.74 | 11 | 0 | 322.74 | 1147.74 | 0
|  | 2.10.1 | beam delivery system design |  | SLAC | Seryi | 5.2 | 702 | 259.74 |  | 0 | 259.74 | 961.74
|  | 2.10.2 | Design of SC magnets for the IR |  | LBNL |  | 0.8 | 112 | 63 | 11 |  | 63 | 186
| 2.11 | Conventional facilities |  |  |  |  | 1.6 | 204 | 70.8915 | 485 | 76.7925 | 147.684 | 836.684 | 0
|  | 2.11.1 | Conventional facility design |  | SLAC | Asiri | 1 | 135 | 49.95 | 100 | 15 | 64.95 | 299.95
|  | 2.11.2 | Conventional facility design |  | FNAL | Kuchler | 0.6 | 69 | 20.9415 | 385 | 61.7925 | 82.734 | 536.734
3 | Research and development | [5 empty] | 106.1 | 14547.65 | 4009.41 | 15331.4 | 2169.1575 | 6508.1675 | 36527.2175 | 105
| 3.1 | Management |  |  |  |  | 1 | 135 | 49.95 | 0 | 0 | 49.95 | 184.95 | 0
|  | 3.1.1 | R&D management |  | SLAC | Markiewicz | 1 | 135 | 49.95 |  | 0 | 49.95 | 184.95
| 3.2 | Global systems |  |  |  |  | 14.25 | 1951.65 | 607.7019 | 1145 | 146.025 | 753.7269 | 3850.3769 | 0
|  | 3.2.1 | High availability power supplies |  | SLAC | Seryi/Larsen | 3.8 | 513 | 189.81 | 455 | 68.25 | 258.06 | 1226.06
|  | 3.2.2 | High availability kicker |  | SLAC | Larsen | 1 | 135 | 49.95 | 100 | 15 | 64.95 | 299.95
|  | 3.2.3 | Diagnostic Processor for power supply |  | SLAC | Bellomo | 0.2 | 27 | 9.99 | 20 | 3 | 12.99 | 59.99
|  | 3.2.4 | High availabilty control system & standard instr. Modules |  | SLAC | Larsen | 6.5 | 877.5 | 324.675 | 345 | 51.75 | 376.425 | 1598.925
|  | 3.2.5 | Development of Universal Accelerator Parser |  | LBNL | Bates | 0.5 | 12.9 | 7.1 |  |  | 7.1 | 20
|  | 3.2.6 | Control Systems |  | ANL | Carwardine | 1.5 | 200 |  | 100 |  |  | 300
|  | 3.2.7 | Time-resolved photon diagnostics |  | ANL | Lumpkin |  | 30 |  | 55 |  |  | 85
|  | 3.2.8 | Survey and alignment |  | ANL | Friedsam |  | 70 |  | 20 |  |  | 90
|  | 3.2.9 | Control System |  | FNAL | Votava | 0.75 | 86.25 | 26.1769 | 50 | 8.025 | 34.2019 | 170.4519
|  | 3.2.10 | Instrumentation |  | FNAL | Wendt | 0.5 | 57.5 | 17.4513 | 30 | 4.815 | 22.2662 | 109.7662
|  | 3.2.11 | Magnets |  | FNAL | Kashikan | 6.75 | 776.25 | 235.5919 | 220 | 35.31 | 270.9019 | 1267.1519
|  | 3.2.12 | Cryogenic System Design |  | FNAL | Peterson | 0.25 | 28.75 | 8.7256 | 0 | 0 | 8.7256 | 37.4756
| 3.3 | Electron sources |  |  |  |  | 7.25 | 978.75 | 362.1375 | 810 | 121.5 | 483.6375 | 2272.3875 | 0
|  | 3.3.1 | Polarized electron source |  | SLAC | Brachmann | 7.25 | 978.75 | 362.1375 | 810 | 121.5 | 483.6375 | 2272.3875
|  | 3.3.1.1 | Photocathode R&D |  |  |  | 2.5 | 337.5 | 124.875 | 200 | 30 | 154.875 | 692.375
|  | 3.3.1.2 | Gun/Injector R&D |  |  |  | 2.75 | 371.25 | 137.3625 | 210 | 31.5 | 168.8625 | 750.1125
|  | 3.3.1.3 | Laser R&D |  |  |  | 2 | 270 | 99.9 | 400 | 60 | 159.9 | 829.9
| 3.4 | Positron sources |  |  |  |  | 4.58 | 1013.5 | 173.275 | 906.4 | 54.75 | 457.625 | 2377.525 | 0
|  | 3.4.1 | NC Positron Capture Structure |  | SLAC | Adolphsen | 0.9 | 121.5 | 44.955 | 90 | 13.5 | 58.455 | 269.955
|  | 3.4.2 | Positron Source |  | SLAC | Sheppard | 1.6 | 216 | 79.92 | 275 | 41.25 | 121.17 | 612.17
|  | 3.4.3 | Positron source target design |  | LLNL | Gronberg | 1.58 | 340 |  | 30 |  | 230 | 600
|  | 3.4.4 | Gamma-ray undulator |  | ANL | Gluskin |  | 250 |  | 500 |  |  | 750
|  | 3.4.5 | Positron Source undulator design |  | LBNL | Sabbi | 0.5 | 86 | 48.4 | 11.4 |  | 48 | 145.4
| 3.5 | Damping rings |  |  |  |  | 2.55 | 410 | 166.92 | 470 | 45 | 211.92 | 1091.92 | 0
|  | 3.5.1 | Electron cloud measurements and PEP-II studies |  | SLAC | Pivi | 1.3 | 175.5 | 64.935 | 200 | 30 | 94.935 | 470.435
|  | 3.5.2 | ATF Ring BPM electronics |  | SLAC | Ross | 0.3 | 40.5 | 14.985 | 100 | 15 | 29.985 | 170.485
|  | 3.5.3 | Damping Rings Studies at LBNL-ALS |  | LBNL | Byrd | 0.75 | 115 | 65 | 11 |  | 65 | 191
|  | 3.5.4 | Development of Time-resolved photon diagnostics |  | ANL | Lumpkin |  | 40 |  | 150 |  |  | 190
|  | 3.5.6 | Higher-order beam diagnostics and tune monitor |  | LBNL |  | 0.2 | 39 | 22 | 9 |  | 22 | 70
| 3.6 | Ring to Main Linac |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.7 | Main Linacs: Optics, beam dynamics, instrumentation |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3.8 | Main Linacs: RF systems |  |  |  |  | 24.45 | 3276 | 1168.6125 | 5002 | 729.285 | 1965.8975 | 10243.8975 | 0
|  | 3.8.1.1 | Marx Modulator |  | SLAC | Leyh | 0 | 0 | 0 | 210 | 31.5 | 31.5 | 241.5
|  | 3.8.1.2 | Marx modulator mechanical engineering |  | LLNL | Gronberg | 0.2 | 42 |  | 130 |  | 28 | 200
|  | 3.8.2 | SC Linac Quad and BPM |  | SLAC | Adolphsen | 0.4 | 54 | 19.98 | 100 | 15 | 34.98 | 188.98
|  | 3.8.3.1 | Coupler development |  | SLAC | Adolphsen | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.8.3.2 | RF coupler test stand development |  | LLNL | Rusnak | 0.25 | 60 |  |  |  | 40 | 100
|  | 3.8.3 | LLRF, RF signal distribution |  | LBNL |  | 1 | 169 | 95 | 22 |  | 95 | 286
|  |  | LLRF Controls |  | FNAL | Carcagno | 4 | 460 | 139.61 | 135 | 21.6675 | 161.2775 | 756.2775
|  | 3.8.4 | Modulators |  | SLAC | Adolophsen | 5.6 | 756 | 279.72 | 690 | 103.5 | 383.22 | 1829.22
|  | 3.8.5 | Klystrons |  | SLAC | Adolphsen | 7.2 | 972 | 359.64 | 3010 | 451.5 | 811.14 | 4793.14
|  | 3.8.6 | RF Distribution |  | SLAC | Adolphsen | 4.8 | 648 | 239.76 | 670 | 100.5 | 340.26 | 1658.26
|  | 3.8.7 | Power coupler assembly and processing |  | SLAC |  | 1 | 115 | 34.9025 | 35 | 5.6175 | 40.52 | 190.52
| 3.9 | Main Linacs: Cavities and Cryomodules |  |  |  |  | 36.7 | 4616.25 | 1363.5869 | 6283 | 1065.585 | 2429.1719 | 13468.4219 | 105
|  | 3.9.1 | TTF2 HOM Monitor |  | SLAC | Ross | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.9.2 | Cavity fabrication |  | FNAL | Foley | 4 | 460 | 139.61 | 2210 | 354.705 | 494.315 | 3164.315
|  |  | EB Welder |  | FNAL | Foley | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.9.2.1 | Cavity EM simulation (HFSS,Omega 3P,GdField,microwave studio) |  | FNAL | Romanov | 0.8 | 92 | 27.922 | 105 | 16.8525 | 44.7745 | 241.7745
|  | 3.9.2.2 | Cavity Cost Reduction |  | FNAL | MOU-MSU | 0.1 | 11.5 | 3.4903 | 200 | 32.1 | 35.5902 | 247.0902
|  | 3.9.3 | 1.3 GHz Cavity BCP @ ANL |  | FNAL | Rowe | 5 | 675 | 249.75 | 50 | 7.5 | 257.25 | 982.25
|  | 3.9.3.1 | BCP and Vertical Testing @ Cornell |  | FNAL | MOU-Cornell | 0.25 | 28.75 | 8.7256 | 200 | 32.1 | 40.8256 | 269.5756
|  | 3.9.3.2 | EP and Vertical Testing @ Jlab |  | FNAL | MOU-Jlab | 0.25 | 28.75 | 8.7256 | 700 | 112.35 | 121.0756 | 849.8256
|  |  | EP Development @ Cornell |  | FNAL | MOU-Cornell | 0.25 | 28.75 | 8.7256 | 150 | 24.075 | 32.8006 | 211.5506
|  | 3.9.3.3 | EP R&D and design study |  | FNAL | Boffo | 2.25 | 258.75 | 78.5306 | 180 | 28.89 | 107.4206 | 546.1706
|  | 3.9.3.4 | EP processing |  | ANL | Kelley |  | 400 |  | 100 |  |  | 500
|  | 3.9.4 | ILC Type IV Cryomodule design |  | FNAL | Peterson | 4 | 460 | 139.61 | 700 | 112.35 | 251.96 | 1411.96
|  | 3.9.5 | Fabrication of test ILC cavities using large/single grain |  | Jlab | Kneisel | 1.2 | 120 | 43 | 130 | 47 | 90 | 340
|  | 3.9.9 | Research in superconducting radiofrequency systems |  | UNIV | Padamsee/Cornell | [6 empty] | 140
|  | 3.9.10 | New cavity shapes and new materials |  | UNIV | Padamsee/Cornell | [7 empty] | 105
|  | 3.9.11 | ILC Cryomodule Value Engineering |  | Jlab | Preble/Rimmer | 0.75 | 75 | 27 | 72 | 26 | 53 | 200
|  | 3.9.12 | Dark current studies |  | Jlab | Reece | 3 | 300 | 108 | 104 | 38 | 146 | 550
|  | 3.9.13 | Multi-layer films |  | Jlab | Phillips | 2 | 200 | 72 | 57 | 21 | 93 | 350
|  | 3.9.14 | SCRF materials research |  | FNAL | Bauer | 6 | 690 | 209.415 | 525 | 84.2625 | 293.6775 | 1508.6775
|  | 3.9.15 | Cryomodule Type IV components (except cavities) |  | FNAL | Peterson | 1 | 115 | 34.9025 | 500 | 80.25 | 115.1525 | 730.1525
|  | 3.9.16 | Finish 3.9 GHz cryomodule |  | FNAL | Harms/Edwards | 3.85 | 442.75 | 134.3746 | 100 | 16.05 | 150.4246 | 693.1746
|  | 3.9.17 | 3.9 GHz crab/deflecting cavities |  | FNAL | Harms/Edwards | 2 | 230 | 69.805 | 200 | 32.1 | 101.905 | 531.905
| 3.1 | Beam delivery system |  |  |  |  | 15.32 | 2166.5 | 117.2262 | 715 | 7.0125 | 156.2388 | 3037.7387 | 0
|  | 3.10.1 | ESA BDS/MDI Expermements |  | SLAC | Tenenbaum | 0.3 | 40.5 | 14.985 | 0 | 0 | 14.985 | 55.485
|  | 3.10.1.1 | ESA BPM Precision Tests - T474
|  | 3.10.1.2 | ESA Collimator wakefield Tests - T480
|  | 3.10.1.3 | ESA Synchrotron rad. spectrometer - T475
|  | 3.10.2 | ATF2 Cavity BPM Electronics |  | SLAC | Ross | 0.3 | 40.5 | 14.985 | 20 | 3 | 17.985 | 78.485
|  | 3.10.3 | Nanometer resolution BPM system |  | LLNL | Walston | 0.22 | 48 |  | 20 |  | 32 | 100
|  | 3.10.4 | Final focus quadrupole full length coil |  | BNL | Annerella | 6 | 1000 |  | 400 |  | 0 | 1400
|  | 3.10.5 | Conceptual design work |  | BNL | Parker | 1.5 | 200 |  |  |  | 0 | 200
|  | 3.10.6 | Beam delivery system-collimators |  | FNAL | Mokhov | 2.5 | 287.5 | 87.2562 | 25 | 4.0125 | 91.2687 | 403.7688
|  | 3.10.7 | Direct wind quench threshold |  | BNL |  |  |  |  | 100 |  |  | 100
|  | 3.10.8 | Vibration R&D |  | BNL |  | 1 | 150 |  | 50 |  |  | 200
|  | 3.10.9 | TDR engineering of FF quad systems |  | BNL |  | 1.5 | 200 |  |  |  |  | 200
|  | 3.10.10 | Laser system development for laser wires |  | LLNL |  | 2 | 200 |  | 100 |  |  | 300
| 3.11 | Conventional facilities |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
4 | Technical Systems engineering and cost estimation in support of RDR | [5 empty] | 13.7 | 1749.5 | 609.0775 | 460 | 71.205 | 680.2825 | 2889.7825 | 0
| 4.1 | Management, technical and engineering services |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.1.1 | Cost and engineering management |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.2 | Vacuum Systems |  |  |  |  | 1.4 | 189 | 69.93 | 0 | 0 | 69.93 | 258.93 | 0
|  | 4.2.1 | Vacuum systems engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.10.5 | BDS cavity, vac, instr system engineering and cost estimation |  | SLAC |  | 1.4 | 189 | 69.93 |  | 0 | 69.93 | 258.93
| 4.3 | Magnet Systems |  |  |  |  | 7.2 | 942 | 337.0688 | 130 | 19.815 | 356.8838 | 1428.8837 | 0
|  | 4.3.1 | Magnet Systems engineering and cost estimation |  | FNAL | Tompkins | 1.5 | 172.5 | 52.3537 | 30 | 4.815 | 57.1688 | 259.6687
|  | 4.3.2 | Positron source engineering and cost estimation |  | SLAC |  | 2 | 270 | 99.9 | 100 | 15 | 114.9 | 484.9
|  | 4.3.3 | BDS Magnet system engineering and cost estimation |  | SLAC |  | 1.2 | 162 | 59.94 |  | 0 | 59.94 | 221.94
|  | 4.3.4 | BDS IR system engineering and cost estimation |  | SLAC |  | 2.5 | 337.5 | 124.875 |  | 0 | 124.875 | 462.375
| 4.4 | Cryomodule |  |  |  |  | 1 | 115 | 34.9025 | 100 | 16.05 | 50.9525 | 265.9525 | 0
|  | 4.4.1 | Cryomodule package engineering and cost estimation |  | FNAL | Stanek | 1 | 115 | 34.9025 | 100 | 16.05 | 50.9525 | 265.9525
| 4.5 | Cavity package |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.5.1 | Cavity package engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.6 | RF power |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.6.1 | RF power engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 4.7 | Instrumentation and Controls |  |  |  |  | 2 | 230 | 69.805 | 80 | 12.84 | 82.645 | 392.645 | 0
|  | 4.7.1 | Instrumentation engineering and cost estimation |  | FNAL | Wendt | 0.75 | 86.25 | 26.1769 | 0 | 0 | 26.1769 | 112.4269
|  | 4.7.2 | Control System engineering and cost estimation |  | FNAL | Votava | 1.25 | 143.75 | 43.6281 | 80 | 12.84 | 56.4681 | 280.2181
| 4.8 | Dumps and collimators |  |  |  |  | 1.6 | 216 | 79.92 | 150 | 22.5 | 102.42 | 468.42 | 0
|  | 4.8.1 | Dumps and collimators engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 4.8.2 | BDS Collimation system engineering and cost estimation |  | SLAC |  | 1.6 | 216 | 79.92 | 150 | 22.5 | 102.42 | 468.42
| 4.9 | Accelerator Physics |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.9.1 | Accelerator physics engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 |  | 0 | 0 | 0
| 4.1 | Industrial Studies |  |  |  |  | 0.5 | 57.5 | 17.4513 | 0 | 0 | 17.4513 | 74.9513 | 0
|  | 4.10.1 | Industrial Studies engineering and cost estimation |  | FNAL | Pfund | 0.5 | 57.5 | 17.4513 |  | 0 | 17.4513 | 74.9513
5 | Infrastructure and test facilities | [5 empty] | 99.35 | 11674 | 3660.87 | 13516.25 | 2155.8086 | 5816.6786 | 31006.9286 | 0
| 5.1 | Management | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| 5.2 | Global systems | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| 5.3 | Electron sources | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| 5.4 | Positron sources | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| 5.5 | Damping rings |  |  |  |  | 0.95 | 150 | 69.97 | 119 | 15 | 84.97 | 353.97 | 0
|  | 5.5.1 | ATF Damping Ring Studies |  | SLAC | Ross | 0.6 | 81 | 29.97 | 100 | 15 | 44.97 | 225.97
|  | 5.5.1.1 | ATF Beam dynamics and instrumentation studies |  |  |  | 0.3 | 40.5 | 14.985 | 50 | 7.5 | 22.485 | 112.985
|  | 5.5.1.2 | ATF multibunch feedback |  |  |  | 0.3 | 40.5 | 14.985 | 50 | 7.5 | 22.485 | 112.985
|  | 5.5.2 | Development of Injection/Extraction Kickers at KEK-ATF |  | LBNL | DeSantis | 0.15 | 30 | 17 | 8 |  | 17 | 55
|  | 5.5.3 | Studies of Beam Dynamics at KEK-ATF |  | LBNL | DeSantis | 0.2 | 39 | 23 | 11 |  | 23 | 73
| 5.6 | Ring to Main Linac | [5 empty] | 0 | 0 |  | 0 | 0 | 0
| 5.7 | Main Linacs: Optics, beam dynamics, instrumentation
| 5.8 | Main Linacs: RF systems |  |  |  |  | 13.75 | 1631.25 | 517.5281 | 2875.25 | 460.0076 | 977.5358 | 5484.0358 | 0
|  | 5.8.1 | 1.3 GHz RF Power Source |  | SLAC | Adolphsen | 1.5 | 202.5 | 74.925 | 40 | 6 | 80.925 | 323.425
|  | 5.8.2 | ILCTA support |  | SLAC | Cassel | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 5.8.2.1 | HA Modulator IGBT Switch array
|  | 5.8.3 | RF Power |  | FNAL | Nagaitsev | 5.25 | 603.75 | 183.2381 | 2370 | 380.385 | 563.6231 | 3537.3731
|  | 5.8.4 | Test Facility LLRF |  | FNAL | Carcagno | 6 | 690 | 209.415 | 365.25 | 58.6226 | 268.0376 | 1323.2876
|  | 5.8.5 | TTF Beam Dynamics and studies |  | SLAC | Ross | 1 | 135 | 49.95 | 100 | 15 | 64.95 | 299.95
| 5.9 | Main Linacs: Cavities and Cryomodules |  |  |  |  | 77.45 | 8920.75 | 2713.7319 | 9872 | 1583.301 | 4297.0329 | 23089.7829 | 0
|  |  | CPF_ANL BCP Facility |  | FNAL | Rowe | 6.1 | 701.5 | 212.9052 | 345 | 55.3725 | 268.2778 | 1314.7777
|  |  | EPF_ANL EP Facility |  | FNAL | Boffo | 3 | 345 | 104.7075 | 875 | 140.4375 | 245.145 | 1465.145
|  |  | Development of Preproduction EP Facility |  | FNAL | Boffo | 3 | 345 | 104.7075 | 150 | 24.075 | 128.7825 | 623.7825
|  | 5.9.1 | MDB Horizontal Test Stand |  | FNAL | Hocker | 1 | 115 | 34.9025 | 50 | 8.025 | 42.9275 | 207.9275
|  |  | IB1 Horizontal Test Stand |  | FNAL | Hocker | 3.25 | 373.75 | 113.4331 | 535 | 85.8675 | 199.3006 | 1108.0506
|  | 5.9.2 | Cavity Vertical Test stand |  | FNAL | Ginsburg | 6.5 | 747.5 | 226.8663 | 350 | 56.175 | 283.0412 | 1380.5412
|  | 5.9.3 | ILCTA_MDB Cryogenics construction |  | FNAL | Theilacker | 1 | 115 | 34.9025 | 88 | 14.124 | 49.0265 | 252.0265
|  | 5.9.4 | ILCTA linac cavity BPM |  | SLAC | Ross | 0.7 | 94.5 | 34.965 | 110 | 16.5 | 51.465 | 255.965
|  | 5.9.5 | Cryomodule Assembly facility |  | FNAL | Arkan | 8 | 920 | 279.22 | 935 | 150.0675 | 429.2875 | 2284.2875
|  | 5.9.6 | ILCTA_NML Facility Infrastructure |  | FNAL | Czarapata | 5 | 575 | 174.5125 | 850 | 136.425 | 310.9375 | 1735.9375
|  | 5.9.7 | ILCTA_NML Cryogenics construction |  | FNAL | Theilacker | 15 | 1725 | 523.5375 | 2774 | 445.227 | 968.7645 | 5467.7645
|  | 5.9.8 | Electron Source for ILCTA |  | FNAL | Nagaitsev | 2 | 230 | 69.805 | 1200 | 192.6 | 262.405 | 1692.405
|  | 5.9.10 | Test Facility Operations |  | FNAL |  | 10 | 1150 | 349.025 | 950 | 152.475 | 501.5 | 2601.5
|  | 5.9.10.1 | ILCTA_NML |  |  | Czarapata | 2.5 | 287.5 | 87.2562 | 300 | 48.15 | 135.4062 | 722.9062
|  | 5.9.10.2 | ILCTA_MDB |  |  | Czarapata | 3.5 | 402.5 | 122.1587 | 350 | 56.175 | 178.3338 | 930.8338
|  | 5.9.10.3 | ILCTA_IB1 |  |  | Carcagno | 4 | 460 | 139.61 | 300 | 48.15 | 187.76 | 947.76
|  | 5.9.11 | Test Facility controls |  | FNAL | Votava | 8.4 | 966 | 293.181 | 340 | 54.57 | 347.751 | 1653.751
|  | 5.9.12 | Test Facility instrumentation |  | FNAL | Wendt | 4.5 | 517.5 | 157.0613 | 320 | 51.36 | 208.4212 | 1045.9213
| 5.1 | Beam delivery system |  |  |  |  | 7.2 | 972 | 359.64 | 650 | 97.5 | 457.14 | 2079.14 | 0
|  | 5.10.1 | Design and Fabrication of magnets for ATF2 |  | SLAC | Seryi | 0.3 | 40.5 | 14.985 | 200 | 30 | 44.985 | 285.485
|  | 5.10.2 | ESA Beamline Instrumentation Upgrade |  | SLAC | Woods/Arnold | 2.8 | 378 | 139.86 | 200 | 30 | 169.86 | 747.86
|  | 5.10.3 | ATF2 Magnet movers |  | SLAC | Ross | 0.3 | 40.5 | 14.985 | 50 | 7.5 | 22.485 | 112.985
|  | 5.10.4 | ATF2 S-band and IP Cavity BPM |  | SLAC | Ross | 0.3 | 40.5 | 14.985 | 80 | 12 | 26.985 | 147.485
|  | 5.10.5 | ESA/LCLS Bunch length monitor |  | SLAC | Ross | 0.5 | 67.5 | 24.975 | 100 | 15 | 39.975 | 207.475
|  | 5.10.6 | ATF2 optics and operations |  | SLAC | Seryi | 3 | 405 | 149.85 | 20 | 3 | 152.85 | 577.85
| 5.11 | Conventional facilities | [10 empty] | 0
6 | Reserve | [11 empty] | 4000 | 1000
| 6.1 | Reserve | [10 empty] | 3000 | 0
|  | 6.1.1 | General reserve |  | DOE/NSF | Grannis | [6 empty] | 3000
| 6.2 | University Accelerator R&D program | [10 empty] | 1000 | 1000
|  | 6.2.1 | FY07 University Accelerator R&D program |  | DOE/NSF | Grannis/Kotcher | [6 empty] | 1000 | 1000
7 | US Bid to host | [5 empty] | 2.5 | 327.5 | 117.3512 | 4700 | 752.25 | 869.6013 | 5897.1012
| 7.1 | Conventional facilities |  |  |  |  | 2 | 270 | 99.9 | 1700 | 270.75 | 370.65 | 2340.65
|  | 7.1.1 | US Bid to Host development at Fermilab |  | FNAL | Kuchler | 0 | 0 | 0 | 1500 | 240.75 | 240.75 | 1740.75
|  | 7.1.2 | US Bid to Host development at SLAC |  | SLAC | Asiri | 2 | 270 | 99.9 | 200 | 30 | 129.9 | 599.9
| 7.2 | Industrial Development |  |  |  |  | 0.5 | 57.5 | 17.4513 | 3000 | 481.5 | 498.9513 | 3556.4513
|  | 7.2.1 | RF Unit fabrication in industry |  | FNAL | Pfund | 0.25 | 28.75 | 8.7256 | 3000 | 481.5 | 490.2256 | 3518.9756
|  | 7.2.2 | RF Unit fabrication in industry |  | SLAC |  | 0.25 | 28.75 | 8.7256 | 0 | 0 | 8.7256 | 37.4756
| 7.3 | U.S. Site Specific Design
|  | 7.3.1 | Program Direction and Admin |  | FNAL | Kephart | 1 | 115 | 34.9025 |  | 0 | 34.9025 | 149.9025
|  | 7.3.1.4 | Public Outreach |  | FNAL | Jackson | 1 | 115 | 34.9025 | 170 | 27.285 | 62.1875 | 347.1875
|  | 7.3.2 | Accelerator design |  | FNAL | Solyak | 4.1 | 471.5 | 143.1002 | 0 | 0 | 143.1002 | 614.6002
|  | 7.3.2.1 | Damping Rings |  | FNAL | Spentzouris | 1.25 | 143.75 | 43.6281 |  | 0 | 43.6281 | 187.3781
|  | 7.3.2.2 | RTML design
|  | 7.3.2.3 | Main linac accelerator physics
|  | 7.3.3 | R&D for U.S. Design ?
|  | 7.3.4 | Technical Systems
vacuum
magnets
|  |  |  | cryogenics layout and design | FNAL | Theilacker | 1 | 115 | 34.9025 | 50 | 8.025 | 42.9275 | 207.9275
8 | Detector | [5 empty] | 21 | 2415 | 732.9525 | 1100 | 176.55 | 909.5025 | 4424.5025
| 8.1 | Detector |  |  |  |  | 21 | 2415 | 732.9525 | 1100 | 176.55 | 909.5025 | 4424.5025
|  | 8.1.1 | Detector |  | FNAL | Demarteau | 14 | 1610 | 488.635 | 950 | 152.475 | 641.11 | 3201.11
|  | 8.1.2 | Test Beam Facility |  | FNAL | Demarteau | 7 | 805 | 244.3175 | 150 | 24.075 | 268.3925 | 1223.3925
etc.
Total | [6 empty] | 279.1 | 36250.9 | 11231.7511 | 36395.85 | 5498.8216 | 17059.9728 | 94459.7228 | 1431
[8 empty] | -------------- |  | Draft budget request |  |  |  | --------------
[8 empty] | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | NSF FY07
[6 empty] | Lab/Univ |  | Labor | Labor | M&S | M&S | Total | Total
[7 empty] | FTE | Direct | Indirect | Direct | Indirect | Indirect
[6 empty] | SLAC | 92.35 | 12447.25 | 4597.835 | 9330 | 1399.8675 | 5997.7025 | 27774.9525 | 0
[6 empty] | FNAL | 186.05 | 21495.75 | 6568.8476 | 26288.25 | 4218.7391 | 10787.5868 | 59044.5868 | 0
[6 empty] | ANL | 4.9 | 1630 | 0 | 1007 | 0 | 0 | 2637 | 0
[6 empty] | Jlab | 6.95 | 695 | 250 | 363 | 132 | 382 | 1440 | 0
[6 empty] | LLNL | 4.25 | 690 | 0 | 280 | 0 | 330 | 1300 | 0
[6 empty] | LBNL | 11.2 | 1951.9 | 1092.5 | 147.6 | 0.2 | 1092.1 | 3191.6 | 0
[6 empty] | BNL | 10 | 1550 | 0 | 550 | 0 | 0 | 2100 | 0
[6 empty] | UNIV | 0 | 0 | 0 | 0 | 0 | 0 | 280 | 431
[6 empty] | DOE/NSF | 0 | 0 | 0 | 0 | 0 | 0 | 4000 | 1000
[6 empty] | BID | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[6 empty] | TOTAL | 315.7 | 40459.9 | 12509.1826 | 37965.85 | 5750.8066 | 18589.3893 | 101768.1392 | 1431
Draft budget request
[8 empty] | -------------- |  | DOE FY07 |  |  |  | --------------
[8 empty] | DOE FY07 | DOE FY07 | M&S | DOE FY07 | DOE FY07 | DOE FY07 | NSF FY07
|  |  |  | MACHINE AREA |  |  |  | Labor | Labor | Direct | M&S | Total | Total
[7 empty] | FTE | Direct | Indirect |  | Indirect | Indirect
|  |  |  | Program direction and administration |  |  | 11.85 | 1481.5 | 508.0925 | 1219 | 186.9855 | 695.078 | 4008.578 | 326
|  |  |  | Management |  |  | 7.8 | 943 | 306.8487 | 250 | 40.125 | 346.9737 | 1539.9738 | 0
|  |  |  | Global systems |  |  | 18.75 | 2559.15 | 832.4769 | 1245 | 161.025 | 993.5019 | 4797.6519 | 0
|  |  |  | Electron sources |  |  | 8.75 | 1181.25 | 437.0625 | 810 | 121.5 | 558.5625 | 2549.8125 | 0
|  |  |  | Positron sources |  |  | 9.08 | 1651 | 298.15 | 948.4 | 54.75 | 582.5 | 3181.9 | 0
|  |  |  | Damping rings |  |  | 15.4 | 2661.25 | 1118.3931 | 725.2 | 68.225 | 1186.4181 | 4572.8681 | 0
|  |  |  | Ring to Main Linac |  |  | 1.2 | 162 | 59.94 | 0 | 0 | 59.94 | 221.94 | 0
|  |  |  | Main Linacs: Optics, beam dynamics, instrumentation |  |  | 7.6 | 934 | 310.4015 | 145 | 23.2725 | 333.674 | 1412.674 | 0
|  |  |  | Main Linacs: RF systems |  |  | 38.2 | 4907.25 | 1686.1406 | 7877.25 | 1189.2926 | 2943.4333 | 15727.9333 | 0
|  |  |  | Main Linacs: Cavities and Cryomodules |  |  | 114.15 | 13537 | 4077.3187 | 16155 | 2648.886 | 6726.2047 | 36558.2047 | 105
|  |  |  | Beam delivery system |  |  | 28.52 | 3952.5 | 799.6063 | 1376 | 104.5125 | 936.1187 | 6264.6187 | 0
|  |  |  | Conventional facilities |  |  | 1.6 | 204 | 70.8915 | 485 | 76.7925 | 147.684 | 836.684 | 0
|  |  |  | Technical Systems |  |  | 13.7 | 1749.5 | 609.0775 | 460 | 71.205 | 680.2825 | 2889.7825 | 0
|  |  |  | Reserve | [8 empty] | 4000 | 1000
|  |  |  | Bid to host |  |  | 2.5 | 327.5 | 117.3512 | 4700 | 752.25 | 869.6013 | 5897.1012 | 0
|  |  |  | TOTAL |  |  | 279.1 | 36250.9 | 11231.7511 | 36395.85 | 5498.8216 | 17059.9728 | 94459.7228 | 1431
Lab | K$/FTE | Indirect-labor | Indirect-M&S
SLAC | 135 | 0.37 | 0.15
FNAL | 115 | 0.3035 | 0.1605
Note on D109: There needs to be a discussion of the effects of not having additional EB Welder capacity available. May want to look for alternative ways to fund this equipment.
Note on D110: split simulation work between cavity EM and Main Linac Studies
Note on D111: investigate TIG welding and hydro-forming of cavities
Note on D116: required to be in a position to specify the next generation EP facility
Note on D146: captured elsewhere 2.1.2 Development of the RDR
Note on D188: includes finish modulator (1.5ms), start new modulator construction for Gun, buy spare parts for modulator, 2 FTE and 550K order 10MW klystron 1000K procure one set of rf distribution hardware for one module + spares (2 FTE and 200K) Reid + tech + new hire build 2 kw drive module (LLRF to Klystron) 1 FTE+120K HTS: procure 500kw klystron 500K 4 2104U klystrons from Titan 200K total
Note on F105: work moved to SLAC
Note on H8: Kephart, Mishra, Stanek, Nagaitsev, Sasse (.5), Konc (.5), Webmaster (1)
Note on H12: .5 Judy Jackson + .5 Public Affairs staff
Note on H17: Moved this to Bid to Host under Public Outreach
Note on H21: Garbincius+(Carter+Peterson+Tompkins all .5)+3 request from PeterG (Primavera expert, WBS person, data entry)
Note on H33: Half of 2.5 FTE identified: Spentzouris 0.3, Amundson 0.3, Stern 0.2, Ivanov 0.2, Ostiguy 0.35, Church 0.25, Johnston 0.2, Ng 0.2, Michelotti 0.5
Note on H49: 4.1 out of 8.2 FTE consisting of: M.Church (70%), F.Ostiguy (65%), J.Jonstone (50%), A.Valishev (80%), V.Lebedev(15%), K.Ranjan(100%), N.Solyak(50%), , P.Lebrune(90%), L.Michelotti (50%), V.Ivanov(80%), P.McBride(55%), P.Spentzouris (15%), Posted Opening 1.0 Asumes this team works half the year on RDR then the other half on US Site Specific design in the TDR
Note on H50: Volk ~0.5 and possibly a student
Note on H58: Kuchler 0.6
Note on H71: 0.75 of 10.4 FTE identified under 5.9.11
Note on H72: 0.5 FTE for this task (1/2 of requested for this work) out of the 6.25 FTE we propose to fund for Instrumentation versus requested 9.5 FTE listed below under 5.9.12
Note on H73: This represents half of the proposed effort by TD to work on Magnet R&D (4/18/06). Rest of work is deferred until FY08
Note on H74: Peterson (.25)
Note on H101: 4 out of 10 FTE identified in 5.8.4
Note on H108: Mike Foley (1.0), Scott Reeves (1.0), Agreement to assign AD Engineer (1.0), AD Technician (1.)
Note on H110: G.Romanov(25%), A.Lunin(30%), T.Khabibulin(25%)
Note on H111: maintain communication and progress reports with institution and make several trips to share knowledge
Note on H112: Allan Rowe, Mike Frett, Debbie Bonifas, Mike Heinz, Ryan Montiel, Wade Muranya, Michael Rauchmiller, Brad Tennis, Dan Assel, Todd Thode, Cristian Boffo, Luciano Elementi, Jamie Blowers, Jan Szal, Contract (2.0), Engineer (2), Drafter (1) These FTEs split between facility work and actual 1.3 GHz processing
Note on H113: maintain communication and progress reports with institution and make several trips to share knowledge
Note on H114: maintain communication and progress reports with institution and make several trips to share knowledge
Note on H115: maintain communication and progress reports with institution and make several trips to share knowledge
Note on H116: C. Boffo 0.25, D. Hicks 0.25, Designer 0.5, C. Antoine 0.25, Associate Scientist 0.25, C. Cooper 0.25, Tech 0.5
Note on H118: Tom Peterson 0.5, Harry Carter 0.25, S.0), Chuck Grimm 0.5 Salman Tariq 0.5, Don Mitchelle 0.8 , Youri Orlov 1.0, Mike McGee 1.0. Peterson 0.2
Note on H125: 6 FTE out of requested 8 FTE Pier Bauer 1.0, C. Antone 0.25, New Bardeen Fellow 1.0, Associate Scientist 1.0, Charlie Cooper 0.25, New Engineer 1.0, F. McConologue 0.5, Drafter 0.5, Tech MDL 0.25, New Tech 1.0
Note on H126: Fabrication Specialist from Materials Control Group and a small part of Peterson
Note on H127: based on 3.9 GHz schedule (Harms)
Note on H128: Leo Bellontoni (1.0) plus partial engineer and partial drafter
Note on H138: Nikolai Mokhov 0.4 Alexandr Drozhdin 0.5 Sergei Striganov 0.6 Noriaki Nakao 1.0
Note on H151: Tompkins .5, Kashikan .5, Tartaglia .5
Note on H156: Independent CM cost estimate team Stanek (counted in Proj Mgmt) Carter 0.1 Peterson 0.1 Pfund 0.15 Kobliska 0.1 Nicol 0.15 Arkan 0.1 Borowski 0.1 Bernstein 0.1 Mitchell 0.1
Note on H158: Jlab responsibility
Note on H162: 0.75 FTE for this task out of the 6.25 FTE we propose to fund versus Requested 9.5 FTE listed below under 5.9.12
Note on H163: 1.25 out of 10.4 FTE identified under 5.9.11
Note on H170: Pfund .2 Kobliska 0.1 Steinke 0.2
Note on H188: Jensen + tech New rf engineer + Reid Ding Sun
Note on H189: 6 out of 10 FTE Ruben Carcagno 0.20, Darryl Orris 0.4, Joe Ozelis 0.1, Andrsei Makulski 0.4, Roger Nehring 0.4, EngII 0.1, Yuriy Pischalnikov 0.3, Jerzy Nogiec 0.1, Dennis Shpakov 0.2, Fred Lewis 0.1, Dan Eddy 0.15, Steve Helis 0.15, others 0.4, Gustavo Cancelo 0.9, Ken Treptow 0.6, Rick Kwarcyany 0.3, Bill Haynes 0.5, Ted Zmuda 0.5, Stefano Rapisarda 0.5, Greg Deuerling 0.3, other Tech 0.4, Brian Chase 0.50, Julien Branlard 0.50, Ed Cullerton 0.5, Tim Koeth 0.5, Mike Kucera 0.5, Dennis Nicklaus 0.5
Note on H192: Allan Rowe, Mike Frett, Debbie Bonifas, Mike Heinz, Ryan Montiel, Wade Muranya, Michael Rauchmiller, Brad Tennis, Dan Assel, Todd Thode, Cristian Boffo, Luciano Elementi, Jamie Blowers, Jan Szal, Contract (2.0), Engineer (2), Drafter (1) These FTEs split between facility work and actual 1.3 GHz processing 3.9.3
Note on H193: C. Boffo 0.25, L. Elementi 0.25, 0.5 Engineering opening, K. Ewald 0.5, 1.5 Tech,
Note on H194: C. Boffo 0.25, L. Elementi 0.25, 0.5 Engineering opening, K. Ewald 0.5, T. Tajima 1.0, C. Antone 0.5
Note on H195: A. Hocker (0.5), New Associate Scientist (0.5), Other work on test stand captured elsewhere including ILCTA_MDB Ops
Note on H196: Clark Reid, Valeriy Poloubotko, Tom Peterson, A. Hocker (0.5), NAS (0.5),
Note on H197: Camille Ginsburg 0.7, Cosmore Sylvester 0.7, Ruben Carcagno, Joe Ozelis, Andrei Lounine, Oleg Prokofiev, Tom Peterson, Valeri Poloubotko, Clark Reid, Charlie Hess, William Mumper, Dean Validis, Danny Massengill, George Krischbaum, Mark Thompson, Craig Lerette, Fred Wilson, Randy Ward, Fred lewis, Steve Helis, Dan Eddy, Yuri Pichalnikov, Darryl Orris, Mike Herr, Chuck Worel, RF Engineer (0.30), ES&H (0.10) includes small percentages of people listed on an as needed basis
Note on H200: Tug Arkan 0.6), Brian Smith (1.0), Marco Battistoni 1.0, Jeff Eliott 1.0, Glen Smith 1.0, Jeff Wittenkeller 1.0, Mark Clebek 1.0, Euvgene Borissov 0.4, Mark Steinke 0.5, John Zweibohmer 0.2, QC 0.2, Process Eng 1.0, Tech 3.0 Move contract techs to M&S
Note on H202: remove 2 engineers to do Site Specific cryo design remove 5 FTE from PPD labor force and replace with contract M&S
Note on H203: Ray Fliller Santucci new laser person (accepted offer)
Note on H204: Work in Progress, will add names
Note on H208: 8.4 FTE for this task out of the 10.4 FTE we propose to fund versus Requested 14.4 FTE Paul Joireman 0.15, Mike Kucera 0.5, Sharon Lackey 0.5,Rich Neswold 0.5,Dennis Nicklaus 0.5,Jerzy Nogiec 0.5,Luciano Piccoli 0.5,Ron Rechenmacher 1.0,Geoff Savage 0.25,Dennis Shpakov 0.5,Vladimir Sirotenko 0.25,Margaret Votava 0.5,Paul Kasley 0.5, Dan Macarthur 0.5, Unidentified AD Controls 2.25,Unidentified CD AMR 1.0,Unidentified AD Sysadmin 0.5 ( Additional Unidentified 4
Note on H209: 4.5 FTE for this task out of the 6.25 FTE we propose to fund versus Requested 9.5 FTE listed below John Van Bogaert 0.25, Charlie Briegel 0.25, Jim Crisp 0.5, Bob Dysert 0.5, Nathan Eddy 0.5, Brian Fellenz 0.25, Jim Fitzgerald 0.25, Marv Olson 0.25, Peter Prieto 0.75, Andrea Saewert 0.25, Alexei Semanov 0.75, John Seraphin 0.25, Randy Thuman-Keup 0.5, Manfred Wendt 0.5, Duane Voy 0.25, Adim Yousif 0.25, Unidentified 3.25
Note on H228: reduce to .25 FTE Pfund (.25)
Note on H232: new person (1)
Note on H233: public affairs staff
Note on H234: 4.1 out of 8.2 FTE consisting of: M.Church (70%), F.Ostiguy (65%), J.Jonstone (50%), A.Valishev (80%), V.Lebedev(15%), K.Ranjan(100%), N.Solyak(50%), , P.Lebrune(90%), L.Michelotti (50%), V.Ivanov(80%), P.McBride(55%), P.Spentzouris (15%), Posted Opening 1.0 Asumes this team works half the year on RDR then the other half on US Site Specific design in the TDR
Note on H235: Half of 2.5 FTE identified: Spentzouris 0.3, Amundson 0.3, Stern 0.2, Ivanov 0.2, Ostiguy 0.35, Church 0.25, Johnston 0.2, Ng 0.2, Michelotti 0.5
Note on H242: Jay, Arkadiy and some portion of other Cryo engineers
Note on K8: Start with 100 (General Ops) + 300 (General travel, non RDR) and add in explicit travel for Controls (70K), Instrumentation (70K), LLRF(36K) + BDS (25K)
Note on K12: communication materials for ILC (50K)
Note on K21: Includes travel associated with RDR (150K) +100K software licenses
Note on K73: HGQ for IR 50K LGQ 50K deferred MLDipole 25K LG HTS Q 35K Electromagnetic tuner 30K Tooling & Cable 30K Superconductor 40K Iron dominated Q 30K deferred Circular coil Q 15K Air core LF Dipole 15K Horiz 2K test cryostat 50K deferred Vertical dewar test st upgrade 25K RT Stretch wire 30K deferred Low fringe magnet field measurements 15K
Note on K74: travel is accounted for under Project Management
Note on K109: deferred 2500K for new EB welder
Note on K111: TIG welding (100K) cavity hydroforming (100K)
Note on K118: 100K for prototype and collaboration + 600K for contract designers
Note on K126: reduced from 1700K buys couplers and some internal parts
Note on K127: based on 3.9 GHz schedule (Harms)
Note on K128: 200K estimate is based on AES order for new cavity design
Note on K156: Simulation software to model process and consultant
Note on K192: remove HPR and add it to CAF Includes 1.3 GHz Mods (125K) + Commissioning for 1.3 GHz (70K) + Handling equipment (125K) + 25K for doc & process control
Note on K193: 450K M&S + 3 FTE ANL Techs
Note on K194: Reduced from 1325K defer until FY08
Note on K198: assumes entire scope of FY06 gets committed by end of year
Note on K200: add in HPR (200K)
Note on K201: build cave (100K), interlocks and electrical infrastructure (130K) and move loading dock (370K) + beam dump (150K) + beamline extension (100K)
Note on K202: add 5 contract people at 120K per year
Note on K203: new laser 200K table upgrade 140K new rf Gun 760K Miscellaneous 100K
Note on K205: cryo operations (250K) + general ops (50K)
Note on K206: cryo operations (300K) + General ops (50K)
Note on K225: 3000K per year start half way through the year
Note on K228: reduce scope of Industrial order for RF unit
Note on K233: 80K for Perspectives Group + communication materials (90K)
Note on K242: cryogenic consultants

## Sheet2
| Requests | Allocations? | FY06
Detectors | 5 | 5 | 0
SLAC | 18 | 17 | 12.3
FNAL | 17.3 | 20 | 11.7 | Does not include RF insfrastructure
ANL | 2.6 | 1 | 0.3
BNL | 2.1 | 1.8 | 0.6
LBNL | 3.1 | 1 | 0.5
LLNL | 1.3 | 1.3 | 1
Jlab | 1.1 | 0.9 | 0.4
Bid-Civil | 3.7 | 3.7 | 0
Bid-Industry | 5 | 5 | 0
Univ | 1.14 | 1.14 | 0.84
Univ (OH) | 0.14 | 0.14 | 0.14
reserve | 2 | 2 | 2
Total | 62.48 | 59.98 | 29.78

## Just FNAL
[8 empty] | -------------- |  | Draft budget request |  |  |  | --------------
[8 empty] | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | DOE FY07 | NSF FY07
[8 empty] | Labor | Labor | M&S | M&S | Total | Total
WBS | Description |  |  |  | Lab/Univ | WP leader | FTE | Direct | Indirect | Direct | Indirect | Indirect
1
| 1.2 | Program management-Fermilab |  |  | FNAL | Kephart | 6 | 690 | 209.415 | 601 | 96.4605 | 305.8755 | 1596.8755
| 1.4 | ILC public relations |  |  | FNAL | Jackson | 1 | 115 | 34.9025 | 50 | 8.025 | 42.9275 | 207.9275
| 1.5 | ILC school |  |  | FNAL | Chou | [6 empty] | 0
| 1.7 | GDE Common fund |  |  | FNAL | Barish | [6 empty] | 473
| 1.9 | Collaboration and outreach |  |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 2.1.2 | Development of the reference design report |  | FNAL | Mishra | 5.5 | 632.5 | 191.9638 | 250 | 40.125 | 232.0888 | 1114.5887
|  | 2.5.2 | Damping ring accelerator physics |  | FNAL | Spentzouris | 1.25 | 143.75 | 43.6281 | 50 | 8.025 | 51.6531 | 245.4031
|  | 2.7.3 | Main linac accelerator physics |  | FNAL | Solyak | 4.1 | 471.5 | 143.1002 | 95 | 15.2475 | 158.3477 | 724.8478
|  | 2.7.4 | Alignment and vibration |  | FNAL | Volk | 0.5 | 57.5 | 17.4513 | 50 | 8.025 | 25.4763 | 132.9762
|  | 2.11.2 | Conventional facility design |  | FNAL | Kuchler | 0.6 | 69 | 20.9415 | 385 | 61.7925 | 82.734 | 536.734
|  | 3.2.9 | Control System |  | FNAL | Votava | 0.75 | 86.25 | 26.1769 | 50 | 8.025 | 34.2019 | 170.4519
|  | 3.2.10 | Instrumentation |  | FNAL | Wendt | 0.5 | 57.5 | 17.4513 | 30 | 4.815 | 22.2662 | 109.7662
|  | 3.2.11 | Magnets |  | FNAL | Kashikan | 6.75 | 776.25 | 235.5919 | 220 | 35.31 | 270.9019 | 1267.1519
|  | 3.2.12 | Cryogenic System Design |  | FNAL | Peterson | 0.25 | 28.75 | 8.7256 | 0 | 0 | 8.7256 | 37.4756
|  |  | LLRF Controls |  | FNAL | Carcagno | 4 | 460 | 139.61 | 135 | 21.6675 | 161.2775 | 756.2775
|  | 3.9.2 | Cavity fabrication |  | FNAL | Foley | 4 | 460 | 139.61 | 2210 | 354.705 | 494.315 | 3164.315
|  |  | EB Welder |  | FNAL | Foley | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 3.9.2.1 | Cavity EM simulation (HFSS,Omega 3P,GdField,microwave studio) |  | FNAL | Romanov | 0.8 | 92 | 27.922 | 105 | 16.8525 | 44.7745 | 241.7745
|  | 3.9.2.2 | Cavity Cost Reduction |  | FNAL | MOU-MSU | 0.1 | 11.5 | 3.4903 | 200 | 32.1 | 35.5902 | 247.0902
|  | 3.9.3 | 1.3 GHz Cavity BCP @ ANL |  | FNAL | Rowe | 5 | 675 | 249.75 | 50 | 7.5 | 257.25 | 982.25
|  | 3.9.3.1 | BCP and Vertical Testing @ Cornell |  | FNAL | MOU-Cornell | 0.25 | 28.75 | 8.7256 | 200 | 32.1 | 40.8256 | 269.5756
|  | 3.9.3.2 | EP and Vertical Testing @ Jlab |  | FNAL | MOU-Jlab | 0.25 | 28.75 | 8.7256 | 700 | 112.35 | 121.0756 | 849.8256
|  |  | EP Development @ Cornell |  | FNAL | MOU-Cornell | 0.25 | 28.75 | 8.7256 | 150 | 24.075 | 32.8006 | 211.5506
|  | 3.9.3.3 | EP R&D and design study |  | FNAL | Boffo | 2.25 | 258.75 | 78.5306 | 180 | 28.89 | 107.4206 | 546.1706
|  | 3.9.4 | ILC Type IV Cryomodule design |  | FNAL | Peterson | 4 | 460 | 139.61 | 700 | 112.35 | 251.96 | 1411.96
|  | 3.9.14 | SCRF materials research |  | FNAL | Bauer | 6 | 690 | 209.415 | 525 | 84.2625 | 293.6775 | 1508.6775
|  | 3.9.15 | Cryomodule Type IV components (except cavities) |  | FNAL | Peterson | 1 | 115 | 34.9025 | 500 | 80.25 | 115.1525 | 730.1525
|  | 3.9.16 | Finish 3.9 GHz cryomodule |  | FNAL | Harms/Edwards | 3.85 | 442.75 | 134.3746 | 100 | 16.05 | 150.4246 | 693.1746
|  | 3.9.17 | 3.9 GHz crab/deflecting cavities |  | FNAL | Harms/Edwards | 2 | 230 | 69.805 | 200 | 32.1 | 101.905 | 531.905
|  | 3.10.6 | Beam delivery system-collimators |  | FNAL | Mokhov | 2.5 | 287.5 | 87.2562 | 25 | 4.0125 | 91.2687 | 403.7688
|  | 4.1.1 | Cost and engineering management |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.2.1 | Vacuum systems engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.3.1 | Magnet Systems engineering and cost estimation |  | FNAL | Tompkins | 1.5 | 172.5 | 52.3537 | 30 | 4.815 | 57.1688 | 259.6687
|  | 4.4.1 | Cryomodule package engineering and cost estimation |  | FNAL | Stanek | 1 | 115 | 34.9025 | 100 | 16.05 | 50.9525 | 265.9525
|  | 4.5.1 | Cavity package engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.6.1 | RF power engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  | 4.7.1 | Instrumentation engineering and cost estimation |  | FNAL | Wendt | 0.75 | 86.25 | 26.1769 | 0 | 0 | 26.1769 | 112.4269
|  | 4.7.2 | Control System engineering and cost estimation |  | FNAL | Votava | 1.25 | 143.75 | 43.6281 | 80 | 12.84 | 56.4681 | 280.2181
|  | 4.8.1 | Dumps and collimators engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 4.9.1 | Accelerator physics engineering and cost estimation |  | FNAL |  | 0 | 0 | 0 |  | 0 | 0 | 0
|  | 4.10.1 | Industrial Studies engineering and cost estimation |  | FNAL | Pfund | 0.5 | 57.5 | 17.4513 |  | 0 | 17.4513 | 74.9513
|  | 5.8.3 | RF Power |  | FNAL | Nagaitsev | 5.25 | 603.75 | 183.2381 | 2370 | 380.385 | 563.6231 | 3537.3731
|  | 5.8.4 | Test Facility LLRF |  | FNAL | Carcagno | 6 | 690 | 209.415 | 365.25 | 58.6226 | 268.0376 | 1323.2876
|  |  | CPF_ANL BCP Facility |  | FNAL | Rowe | 6.1 | 701.5 | 212.9052 | 345 | 55.3725 | 268.2778 | 1314.7777
|  |  | EPF_ANL EP Facility |  | FNAL | Boffo | 3 | 345 | 104.7075 | 875 | 140.4375 | 245.145 | 1465.145
|  |  | Development of Preproduction EP Facility |  | FNAL | Boffo | 3 | 345 | 104.7075 | 150 | 24.075 | 128.7825 | 623.7825
|  | 5.9.1 | MDB Horizontal Test Stand |  | FNAL | Hocker | 1 | 115 | 34.9025 | 50 | 8.025 | 42.9275 | 207.9275
|  |  | IB1 Horizontal Test Stand |  | FNAL | Hocker | 3.25 | 373.75 | 113.4331 | 535 | 85.8675 | 199.3006 | 1108.0506
|  | 5.9.2 | Cavity Vertical Test stand |  | FNAL | Ginsburg | 6.5 | 747.5 | 226.8663 | 350 | 56.175 | 283.0412 | 1380.5412
|  | 5.9.3 | ILCTA_MDB Cryogenics construction |  | FNAL | Theilacker | 1 | 115 | 34.9025 | 88 | 14.124 | 49.0265 | 252.0265
|  | 5.9.5 | Cryomodule Assembly facility |  | FNAL | Arkan | 8 | 920 | 279.22 | 935 | 150.0675 | 429.2875 | 2284.2875
|  | 5.9.6 | ILCTA_NML Facility Infrastructure |  | FNAL | Czarapata | 5 | 575 | 174.5125 | 850 | 136.425 | 310.9375 | 1735.9375
|  | 5.9.7 | ILCTA_NML Cryogenics construction |  | FNAL | Theilacker | 15 | 1725 | 523.5375 | 2774 | 445.227 | 968.7645 | 5467.7645
|  | 5.9.8 | Electron Source for ILCTA |  | FNAL | Nagaitsev | 2 | 230 | 69.805 | 1200 | 192.6 | 262.405 | 1692.405
|  | 5.9.10 | Test Facility Operations |  | FNAL |  | 10 | 1150 | 349.025 | 950 | 152.475 | 501.5 | 2601.5
|  | 5.9.11 | Test Facility controls |  | FNAL | Votava | 8.4 | 966 | 293.181 | 340 | 54.57 | 347.751 | 1653.751
|  | 5.9.12 | Test Facility instrumentation |  | FNAL | Wendt | 4.5 | 517.5 | 157.0613 | 320 | 51.36 | 208.4212 | 1045.9213
|  | 7.1.1 | US Bid to Host development at Fermilab |  | FNAL | Kuchler | 0 | 0 | 0 | 1500 | 240.75 | 240.75 | 1740.75
|  | 7.2.1 | RF Unit fabrication in industry |  | FNAL | Pfund | 0.25 | 28.75 | 8.7256 | 3000 | 481.5 | 490.2256 | 3518.9756
|  | 7.3.1 | Program Direction and Admin |  | FNAL | Kephart | 1 | 115 | 34.9025 |  | 0 | 34.9025 | 149.9025
|  | 7.3.1.4 | Public Outreach |  | FNAL | Jackson | 1 | 115 | 34.9025 | 170 | 27.285 | 62.1875 | 347.1875
|  | 7.3.2 | Accelerator design |  | FNAL | Solyak | 4.1 | 471.5 | 143.1002 | 0 | 0 | 143.1002 | 614.6002
|  | 7.3.2.1 | Damping Rings |  | FNAL | Spentzouris | 1.25 | 143.75 | 43.6281 |  | 0 | 43.6281 | 187.3781
|  |  |  | cryogenics layout and design | FNAL | Theilacker | 1 | 115 | 34.9025 | 50 | 8.025 | 42.9275 | 207.9275
|  | 8.1.1 | Detector |  | FNAL | Demarteau | 14 | 1610 | 488.635 | 950 | 152.475 | 641.11 | 3201.11
|  | 8.1.2 | Test Beam Facility |  | FNAL | Demarteau | 7 | 805 | 244.3175 | 150 | 24.075 | 268.3925 | 1223.3925
[7 empty] | 186.05 | 21495.75 | 6568.8476 | 26288.25 | 4218.7391 | 10787.5868 | 59044.5868