## Sheet1
CTA09 Proposed R&D Topics for the Remainder of the CesrTA Program
Session: 1
Conveners: K. Harkay, Y. Suetsugu, R. Zwaska
Topics: EC Build-up and Mitigation I and II
R&D Class | R&D Task Description | Pre-requisites | Deliverables | Priority† | Participants | Target Date‡
EC Build-up | Characterization of SE - Define beam measurements that provide input for SE parameters |  | Data for EC dynamics simulation | Critical | C. Celata, J. Crittenden, others | 2009/12
EC Build-up | Define and carry out experiments to determine PE properties, analyze data |  | Data for EC dynamics simulation | Critical | G. Dugan, D. Sagan, K. Harkay, J. Livezy | 2009/12
EC Build-up | Guidebook for understanding and using SEY and parametrizations |  | Data for EC dynamics simulation | Very high | M. Furman, G. Rumolo | 2009/12
EC Build-up | Measurement and analysis of EC in quadrupole | RFA in quadruple | Data for EC dynamics simulation | Very high | K. Kanazawa, Y. Li | 2009/12
EC Build-up | In-situ SEY characterization with ECLOUD1 (Al, Cu, SS, coatings) |  | Data for EC dynamics simulation, mitigation | Very high | S. Greenwald, R. Zwaska, others | 2010/3
EC Build-up | Surface conditioning - Beam studies and analysis of surface conditioning (SS, Cu, Al, coatings) (time evolution) | Enough operation time | Data for EC dynamics simulation | High | R. Zwaska, J. Livezey, others | 2010/7
EC Build-up | EC lifetime measurement with witness bunches; find SEY @ E=0; time evolution | Periodic Measurements | Data for EC dynamics simulation | High | Cornell team | 2010/3
EC Build-up | Multipacting threshold bunch current (PE vs SE dominated) (vs. vacuum pressure rise?) |  | Data for EC dynamics simulation | Moderate | Cornell team | 2010/3
EC Build-up | Carry out machine studies to compare component surfaces (SS, copper, Al, etc.) | Material choice of DR | Data for EC dynamics simulation | Moderate | Cornell team | 2010/7
RFA | Modeling of RFA as part of the EC system (resonance due to SE from grid) |  | Incorporate RFA model into buildup codes | Critical | J. Calvey, M. Venturini | 2009/8
RFA | Estimation of electron density | RFA modeling | Evaluation of electron density | Very high | K. Kanazawa | 2009/12
RFA/ TE Wave | Correlate RFA with TE wave measurement in drifts and bends | Calibration of TE wave measurement | Validation of instrumentation | Very High | S. De Santis, J. Sikora, (N. Eddy, CY Tan)? | 2009/8
TE wave | TE wave vs. resonant BPM; time resolved |  |  | Very high | S. De Santis, J. Sikora | 2010/3
RFA/ TE Wave | Devise a plan for correlating RFA with TE wave measurements in a wiggler; time structure (EC at BY=0 has longer lifetime) | Calibration of TE wave measurement | Validation of instrumentation | High | S. De Santis, J. Sikora | 2010/3
Instrumentation | Investigate shielded electrode for wiggler measurements or other |  | New instrumentation possibility | Moderate | S. De Santis, J. Sikora, M. Billing, M. Palmer | 2010/3
Mitigation | Determine best techniques for general mitigation strategy |  |  | Critical | Y. Suetsugu, M. Pivi | 2010/3
Mitigation | Mitigation in wiggler: Cu Groove (TiN coated) | New wiggler beam pipe |  | Critical | M. Pivi, Y. Li | 2009/8 (2010/3)
Mitigation | Mitigation in wiggler: Clearing electrode | New wiggler beam pipe |  | Very high | Y. Suetsugu, Cornell team | 2009/12
Mitigation | Mitigation in straight: Enamel electrode | New beam pipe |  | Very high | B. Zwaska | 2009/12
Mitigation | Long term reliability of electrodes and coatings | Enough operation time |  | High | M. Palmer | 2010/3
Mitigation | Alpha-carbon |  | SPS | High | “CERN” | 2010/3
Mitigation | NEG coating |  |  | Very High | M. Pivi | 2010/3
Mitigation | Mitigation in wiggler: Enamel electrode | New wiggler beam pipe |  | Moderate | B. Zwaska | 2010/3
Mitigation | Solenoid field |  |  | Moderate |  | 2010/7
Mitigation | Beam pipe with photon absorption (roughness), PE trapping |  |  | Moderate |  | 2010/3
Mitigation | Beam pipe with antechamber |  |  | Low |  | 2010/7
*R&D Classifications: eg, LET, Instrumentation, RFA, TE Wave, EC Simulation, xBSM, Other
†Priority Classifications: Critical, Very High, High, Moderate, Low
‡Specify first run period when measurement can be accomplished or nominal date when simulations/analysis could be made available.