## EC-simulations
CTA09 Proposed R&D Topics for the Remainder of the CesrTA Program
Session: Electron cloud simulations
Conveners: G. Dugan. J. Flanagan
R&D Class | R&D Subcategory | Task Description | Pre-requisites | Deliverables | Priority | Priority rank | Participants | Target Date
EC simulation | all simulations | Estimate of the scattered radiation around the CESR ring. This will need X-ray scattering and absorption data for guidance | X-ray scattering data | X-ray data summary; modified SYNRAD program | Critical | 1 | G. Dugan, D. Sagan, K. Harkay | 2009-08-01
EC simulation | RFA simulations | include the details of the RFA structure itself into the cloud simulation programs. | RFA device models | Revised versions of POSINST, WARP/POSINST, and ECLOUD | Critical | 1 | M. Venturini, J. Calvey, J. Livezey, J. Crittenden, C. Celata, J-L. Vay (WARP) | 2009-09-01
EC simulation | RFA simulations | Run simulations for the existing RFA drift and dipole data sets for a range of cloud physics parameters, to establish the best fit ranges of these parameters for different surfaces and mitigation techniques. Correlate with in-situ SEY measurements and parameters found from ringwide coherent tune shift fits. | Revised versions of POSINST and ECLOUD incorporating RFA's; Automation scripts and documentation | Best fit estimates of cloud physics parameters for each RFA surface or mitigation technique in drifts and dipoles. Comparisons with SEY measurements and ringwide average parameter fits. | Critical | 1 | G. Dugan, D. Kreinick, students | 2009-09-01
EC simulation | RFA simulations | Run simulations for the existing RFA wiggler data sets for a range of cloud physics parameters, to establish the best fit ranges of these parameters for different surfaces and mitigation techniques in the wigglers. | Revised version of WARP/POSINST incorporating RFA's | Best fit estimates of cloud physics parameters for each RFA surface or mitigation technique in the wigglers | Critical | 1 | C. Celata,J. Calvey, G. Penn | 2009-10-01
EC simulation | RFA simulations | identify experimentally accessible signatures of the structure of the cloud in the By=0 wiggler regions. | None | Proposed experiment to probe cloud in wiggler By=0 regions | Critical | 1 | ? | ?
EC simulation | Coherent tune shift simulations | Run simulations for the existing data sets for a range of cloud physics parameters describing the ringwide drifts and dipoles, to establish the best fit ranges of these parameters. | Automation scripts and documentation | Best fit estimates of cloud physics parameters in ringwide drifts and dipoles | Critical | 1 | G. Dugan, D. Kreinick | 2009-08-01
EC simulation | RFA simulations | Develop a procedure for automating the (2D) simulation of a given RFA data set. | RFA database | Automation scripts and documentation | Critical | 1 | G. Dugan, D. Kreinick | 2009-08-01
EC simulation | Coherent tune shift simulations | automate the calculation of tune shifts from drifts and dipoles performed with and without coherent motion of the whole train. | None | Automation scripts and documentation | Critical | 1 | G. Dugan, D. Kreinick | 2009-07-01
EC simulation | all simulations | Develop an improved photoelectron model (quantum efficiency, photoelectron energy, angular spectra, effect of fluorescence) based on existing data, with measurements if needed | Photoemission data; photoemission measurements? | Modified photoemission model incorporated into POSINST | Very High | 2 | G. Dugan, D. Sagan, K. Harkay | 2009-09-01
EC simulation | all simulations | Using simulations, define set of experiments (RFA, TE wave, tune shift) which can be done at CesrTA that can independently determine the key electron cloud physics paramters. | None | List of experiments and the related key electron cloud physics parameters | Very High | 2 | C. Celata, J. Crittenden, M. Furman, K. Harkay | 2009-09-01
EC simulation | TE wave simulations | Simulate cloud densities sampled by TE wave measurements | Definition of longitudinal regions sampled by TE wave measurements | Cloud densities averaged over longitudinal regions sampled by TE wave experiments | Very high | 2 | ? | ?
EC simulation | TE wave simulations | Compute effect of nonuniform cloud distrbution on TE wave phase shifts in the presence of magnetic field | Cloud densities averaged over longitudinal regions sampled by TE wave experiments | Estimates of TE wave phase shifts produced by electron cloud | Very high | 2 | ? | ?
EC simulation | Coherent instabilities | Estimate the threshold, growth time and mode spectrum for multibunch instabilities at CesrTA. Consider witness bunch configurations as well as train measurements. | Cloud densities derived from tune shfit measurements | threshold, growth time and mode spectrum for multibunch instabilities at CesrTA. | Very high | 2 | K. Ohmi, M. Pivi | 2009-08-01
EC simulation | Coherent instabilities | estimate the threshold for the head-tail instability at CesrTA. Consider witness bunch configurations as well as train measurements. | Cloud densities derived from tune shfit measurements | threshold for the head-tail instability at CesrTA. | Very high | 2 | K. Ohmi, M. Pivi | 2009-08-01
EC simulation | Sub-threshold incoherent emittance growth | Estimate the expected level of incoherent emittance growth at CesrTA for positrons and electrons. Consider witness bunch configurations as well as train measurements to control better the cloud density. | Cloud densities derived from tune shfit measurements | Estimate of expected incoherent emittance growth at CesrTA | Very high | 2 | K. Ohmi, M. Pivi | 2009-08-01
EC simulation | RFA simulations | develop capability to simulate cloud and RFA in quadrupole | Quadrupole RFA device model | WARP/POSINST version with RFA and/or quadrupole or CLOUDLAND with quadrupole RFA model | High | 3 | C. Celata, J-L. Vay, J. Calvey | 2009-12-01
EC simulation | RFA simulations | Run simulations for the RFA quadrupole data sets for a range of cloud physics parameters, to establish the best fit ranges of these parameters for different surfaces and mitigation techniques. | Revised code incorporating RFA | Best fit estimates of cloud physics parameters in quadrupole | High | 3 | C. Celata, J-L. Vay | 2009-12-01
EC simulation | RFA simulations | resolve discrepancies between simulation codes regarding the structure of the cloud in the By=0 regions | None | Benchmarking runs of CLOUDLAND and WARP/POSINST with 3D wiggler model | High | 3 | C. Celata, L. Wang | 2009-10-01
EC simulation | Coherent tune shift simulations | estimate contributions to tune shifts from wigglers and quadrupoles. | WARP/POSINST quadrupole code | Estimates of tune shift contributions from typical CESR quadrupole and wiggler | High | 3 | ? | ?
EC simulation | Coherent tune shift simulations | develop estimates of cloud-induced betatron phase advances over sections of the ring. | None | Specification of optimal regions of ring for betatron phase measurements, to distinguish drift and dipole cloud contributions | High | 3 | ? | ?
*R&D Classifications: eg, LET, Instrumentation, RFA, TE Wave, EC Simulation, xBSM, Other
†Priority Classifications: Critical (1), Very High (2), High (3), Moderate (4), Low (5)
‡Specify first run period when measurement can be accomplished or nominal date when simulations/analysis could be made available.

## EC-beam-cloud experiments
CTA09 Proposed R&D Topics for the Remainder of the CesrTA Program
Session: Electron cloud simulations
Conveners: G. Dugan. J. Flanagan
R&D Class | R&D Subcategory | Task Description | Pre-requisites | Deliverables | Priority | Priority rank | Participants | Target Date
Beam-cloud experiments | Coherent tune shifts | Complete reprocessing of older tune shift data from Nov 08 and Jan 09 runs. | None | All tune shift data files in standard format | Critical | 1 | D. Kreinick | 2009-07-01
Beam-cloud experiments | Coherent tune shifts | Develop techniques and software to process tune shift data from Dimtel feedback system; process data from June 09 run. | None | Programs and scripts to convert Dimtel tune measurements to tune shift data files in standard format. | Critical | 1 | G. Dugan, D. Kreinick, ? | 2009-07-01
Beam-cloud experiments | Coherent tune shifts | Process Dimtel data from June 09 run. | Programs and scripts to convert Dimtel tune measurements to tune shift data files in standard format. | June 09 tune shift data in standard format. | Critical | 1 | G. Dugan, D. Kreinick | 2009-07-01
Beam-cloud experiments | Coherent tune shifts | Develop software to process tune shift data and multibunch mode spectra from new BPM system. | Definition of data structures for new BPM system | Programs and scripts to convert new BPM tune measurements to tune shift data files in standard format. | Critical | 1 | ? | 2009-07-01
Beam-cloud experiments | Coherent tune shifts | Make witness bunch and train current dependence measurements with 4, 8, 12, 16 ns using Dimtel system. Make measurements with pinger on, all bunches damped except one. | Programs and scripts to convert Dimtel tune measurements to tune shift data files in standard format. | Tune shift data files in standard format, corresponding to witness bunch and train current dependence measurements with 4, 8, 12, 16 ns, individual bunch excitation. | Critical | 1 | G. Dugan, ? | July-August CesrTA run
Beam-cloud experiments | Coherent tune shifts | Make witness bunch and train current dependence measurements, with 4, 8, 12, 16 ns using the new BPM system, with existing (full train) pingers. Cross check with Dimtel system measurements. | Programs and scripts to convert new BPM tune measurements to tune shift data files in standard format. | Tune shift data files in standard format, corresponding to witness bunch and train current dependence measurements with 4, 8, 12, 16 ns, full train excitation | Critical | 1 | G. Dugan, ? | July-August CesrTA run
Beam-cloud experiments | Incoherent emittance growth | Use X-ray beam size monitor to measure growth of vertical emittance vs. bunch number in trains of positrons and electrons at 2 and 5 GeV, at various bunch spacings and currents. (Check that there is no coherent signal.) Repeat this at different working points. | Software to analyze XBSM data | Characterization of incoherent emittance growth vs. cloud conditions | Critical | 1 | K. Ohmi, J. Flanagan, M. Pivi | November-December CesrTA run
Beam-cloud experiments | Coherent tune shifts | Develop method to use Dimtel system to damp all bunches but one, excite this bunch with shaker and measure tune. Automate. | None | Automation scripts for Dimtel system to allow excitation and tune measurement of single bunches. | Very high | 2 | ? | July-August CesrTA run
Beam-cloud experiments | Coherent tune shifts | Make witness bunch and train current dependence measurements, using the new BPM system to make betatron phase advance meaurements as a function of bunch number. | Programs and scripts to convert new BPM tune measurements to tune shift data files in standard format. | Betatron phase advance measurements of selected regions | Very high | 2 | G. Dugan, ? | November-December CesrTA run
Beam-cloud experiments | Coherent instabilities | Use new BPM system to observe threshold and modes of coherent multi-bunch instabilities at 4, 8, 12, 16 ns as a function of cloud configuration and feedback settings | Programs and scriptsfor mode analysis from new BPM tune measurements. | Characterization of threshold and mode of cloud-driven multibunch instabilties | Very high | 2 | K. Ohmi, J. Flanagan, M. Pivi | July-August CesrTA run
Beam-cloud experiments | Coherent instabilities | Establish appropriate cloud conditions for head-tail instability and measure threshold (via synchrobetatron sideband enhancement using BPM system and feedback system) and measure centroid and size variations with XBSM monitor. Vary chromaticity , beam current, working point. | Software to analyze BPM data for synchrobetatron motion, and to analyze XBSM data. | Characterization of threshold and emittance growth due to cloud-driven head-tail instability | Very high | 2 | K. Ohmi, J. Flanagan, M. Pivi | July-August CesrTA run
Beam-cloud experiments | Incoherent tune spectrum | Scan working point and measure distance in tune space from center of tune distribution to resonance lines? Use incoherent Schottky spectrum? (F. Caspers) | ? | Characterization of incoherent tune spectrum vs. bunch number | High | 3 | ? | ?
*R&D Classifications: eg, LET, Instrumentation, RFA, TE Wave, EC Simulation, xBSM, Other
†Priority Classifications: Critical (1), Very High (2), High (3), Moderate (4), Low (5)
‡Specify first run period when measurement can be accomplished or nominal date when simulations/analysis could be made available.