## Slide 1: ILC Damping Ring Activities Cornell Group
Mark Palmer
GDE

## Slide 2: ART Budget Breakdown
Total FTEs in Revised Budget: ~5.5 FTEs
DR Technical Area Group Mgmt: 0.25 FTE (Palmer)
DR Lattice Design and Physics Studies
  Sr Personnel 0.5 FTE
  GRA 0.75 FTE
Electron Cloud: Mitigation Implementation Plan, Ongoing Studies (eg, durability tests and sub-threshold emittance growth studies at progressively lower ey), Simulations (particularly baseline lattice characterization and high power option studies)
  Sr Personnel 2.25 FTE
  GRA 0.75 FTE
  Technician 1 FTE

## Slide 3: Updates
Baseline Lattice now Cornell design
  Situation seriously constrained by manpower limitations
Much of CFS and design interfacing defaulting to Cornell
  Would like to add ~0.5 FTE designer time in order to make this more effective (and accurate) as well as more manageable
  Principal tasks
    Take Cockroft generated models and…
      Update for new baseline
      Expand for completely revamped vacuum system (needed for costing as well) and new magnet specs
      Confirm CFS assumptions (eg, eliminate conservatism leading to outsized tunnel, etc)
    Help with Sources-DR interface and DR-RTML interface layout constraints
    Help document EC mitigation plans in vacuum system (sketch/simple model level)

## Slide 4: Revised Direction
Minimize any further EC R&D and direct available resources towards DR design activities due to resource limitations around the world
  Implications: Reduce technician time since that is directed primarily at ongoing EC R&D
  Ensure that sufficient design resources are available for DR Lattice design, documentation and costing effort
    Requires engineering layout support
    Updated magnet systems conceptual plan and costing
  Ensure that resources are available for remaining EC evaluations for the new DR baseline design
  Ensure that vacuum system conceptual design and costing can be completed (discussed option to obtain SuperKEKB costs)
  Mechanical designer effort is desirable in the context of lost UK resources. Very useful for completing the new 3.2km baseline ring conceptual design and basic costing
Mike Harrison
  Has provided some $$ support
  Minimize direct hardware effort

## Slide 5: Our Nominal Manpower Breakdown
Total FTEs: ~6
Management: ~0.25 FTEs total
Damping Ring Design Tasks: ~2.75 FTEs total
  Lattice-related: ~1.25
  Supporting Design/Costing (eg. magnet system): ~1.5
Electron Cloud Tasks: ~3.0 FTEs total
  Electron cloud evaluations: ~1.5
  Conceptual implementation of mitigations and vacuum system design/costing: ~1.5

## Slide 6: Top-Level Timeline as Reviewed at ALCPG11
Some push-back to move earlier

## Slide 7
Updated DR Timeline

## Slide 8: Resources
Lattice Design – Cornell (+IHEP)
Layout - Cornell
RF Specifications – Frascati
Magnets & PS – Cornell + SLAC(?)
Instrumentation – FNAL + ???
Vacuum – Cornell + KEKB(?) + Frascati + ???
  Overall concept
  EC Mitigation Implementation
Physics Studies
  EC: SLAC, Frascati, LBNL, CU, ANL, …
  FII: Guoxing Xia
  Other: TBD
CFS – FNAL
TDR Preparations (coord) – Frascati + Cornell + …

## Slide 9: Our ILCDR WBS
ILC Damping Rings WBS - Version Date: |  |  |  |  |  |  |  |  | 9/1/11 |  | 
WBS |  |  |  |  | Acct | Acct | Proj/ | Category | Replicon Category | Coordinator | Work Description
 |  |  |  |  | Type | Number | Duo |  |  | * = CAM | 
1 |  |  |  |  |  | TBD | 100-000 | INTERNATIONAL LINEAR COLLIDER DAMPING RINGS ACTIVITIES | ILCDR_1 ILC Damping Rings | M. Palmer* | Activities in support of the ILC Damping Rings technical design
1 | 1 |  |  |  | DOE Non-Cap | TBD | 101-000 | Project Administration | ILCDR_1.1 Proj Admin |  | All ILC Damping Ring administrative activities including GDE and ART involvement.
1 | 1 | 1 |  |  | DOE NC |  | 101-100 | Damping Rings Area Group Management | ILCDR_1.1 Proj Admin | M. Palmer | Management and participation in the ILC Damping Rings Area Group
1 | 1 | 2 |  |  | DOE NC |  | 101-200 | Americas Regional Team Management | ILCDR_1.1 Proj Admin | M. Palmer | Management activities for the ILC Americas Regional Team
1 | 1 | 3 |  |  | DOE NC |  | 101-300 | Workshop/Conference Support | ILCDR_1.1 Proj Admin | M. Palmer | ILC Damping Rings Workshop and Conference support activities.
1 | 2 |  |  |  | DOE Non-Cap | TBD | 102-000 | DR Design Support | ILCDR_1.2 DR Design |  | ILC Damping Rings design activities including lattice and machine design as well as area group and GDE reporting tasks.
1 | 2 | 1 |  |  | DOE NC |  | 102-100 | Lattice Design and Characterization | ILCDR_1.2 DR Design | D. Rubin | ILC DR lattice design and characterization activities
1 | 2 | 1 | 1 |  | DOE NC |  | 102-110 | DTC Lattice Design | ILCDR_1.2 DR Design | D. Rubin | Development of the DTC Baseline Lattice
1 | 2 | 1 | 2 |  | DOE NC |  | 102-120 | DTC Lattice Characterization | ILCDR_1.2 DR Design | J. Crittenden | Characterize the Physics Performance for the TDR Baseline Lattice
1 | 2 | 1 | 3 |  | DOE NC |  | 102-130 | Reporting | ILCDR_1.2 DR Design | M. Palmer | Coordinate Cornell Contributions to ILC GDE Report Structure for ILC TDP-II
1 | 2 | 2 |  |  | DOE NC |  | 102-200 | Technical Design Activities | ILCDR_1.2 DR Design | M. Palmer | ILC DR Technical Systems design and support activities including system specifications and design efffort (eg, electron cloud mitigation development, vacuum system support, instrumentation specifications, etc)
1 | 2 | 2 | 1 |  |  |  | 102-210 | Vacuum System | ILCDR_1.2 DR Design | Y. Li | Incorporate EC Mitigations into ILC DR Vacuum Design and Participate in Overall System Design and Costing
1 | 2 | 2 | 2 |  |  |  | 102-220 | Magnet System | ILCDR_1.2 DR Design | M. Palmer | Magnet System Design and Costing
1 | 2 | 2 | 3 |  | DOE NC |  | 102-230 | Instrumentation | ILCDR_1.2 DR Design | M. Billing | Instrumentation System Updates and Costing
1 | 2 | 2 | 4 |  |  |  | 102-240 | ILC Central Region Interface | ILCDR_1.2 DR Design | M. Palmer | ILC Central Region Design and Interface
1 | 2 | 2 | 5 |  |  |  | 102-250 | ILC CF&S Interface | ILCDR_1.2 DR Design | M. Palmer | Damping Ring Interface to the Conventional Facilities & Siting Group
1 | 3 |  |  |  | DOE Fab | TBD | 103-000 | Hardware Development | ILCDR_1.3 Hardware Devel |  | Hardware prototyping for the ILC damping rings using CesrTA
1 | 3 | 1 |  |  | DOE Fab | TBD | 103-100 | Instrumentation Development Using CESR | ILCDR_1.3 Hardware Devel | M. Palmer | Bunch-by-bunch & turn-by-turn beam size monitor development. Development to be carried out at CesrTA.
1 | 3 | 2 |  |  | DOE Fab | TBD | 103-200 | EC Mitigation Development Using CESR | ILCDR_1.3 Hardware Devel | M. Palmer | Electron cloud mitigation development and vacuum chamber prototyping. Development to be carried out at CesrTA.
Essentially all effort now concentrated in WBS 1.1 and 1.2!

## Slide 10: DTC Lattice Work (WBS 1.2.1.1)
All items are, more or less, critical path
  1.2.1.1.1-4 are critical for finalizing the DR specifications and getting simulators in business – hoping for additional progress before LCWS11
  1.2.1.1.5 is a particular concern due to interactions with ILC Central Region Layout – will also get attention at LCWS11
  1.2.1.1.5-6 are somewhat less critical
1 | 2 | 1 |  |  | DOE NC |  | 102-100 | Lattice Design and Characterization | ILCDR_1.2 DR Design | D. Rubin | ILC DR lattice design and characterization activities
1 | 2 | 1 | 1 |  | DOE NC |  | 102-110 | DTC Lattice Design | ILCDR_1.2 DR Design | D. Rubin | Development of the DTC Baseline Lattice
1 | 2 | 1 | 1 | 1 | DOE NC |  | 102-111 | Baseline Lattice | ILCDR_1.2 DR Design | DLR/WD | General lattice design including relationship between stacked rings
1 | 2 | 1 | 1 | 2 | DOE NC |  | 102-112 | Wiggler-RF Straight Optics/Layout | ILCDR_1.2 DR Design | DLR/MAP | Design refinement of the RF-wiggler straights including relationship between stacked rings
1 | 2 | 1 | 1 | 3 | DOE NC |  | 102-113 | Injection-Extraction Straight Optics/Layout | ILCDR_1.2 DR Design | DLR/MAP | Design refinement of the injection/extraction straights including relationship between stacked rings.
1 | 2 | 1 | 1 | 4 | DOE NC |  | 102-114 | Harmonic Number Adjustment | ILCDR_1.2 DR Design | DLR/WD | Adjust ring harmonic number for overall ILC compatibility
1 | 2 | 1 | 1 | 5 | DOE NC |  | 102-115 | Injection/Extraction Line Design | ILCDR_1.2 DR Design | DLR/JSh | Injection and extraction lines from the DR to the entrance of the ELTR/PLTR tunnels
1 | 2 | 1 | 1 | 6 | DOE NC |  | 102-116 | Wiggler Requirements | ILCDR_1.2 DR Design | DLR/MAP | Updated wiggler requirements for new damping ring baseline and overall ILC operating modes
1 | 2 | 1 | 1 | 7 | DOE NC |  | 102-117 | Momentum Compaction Adjustments/Flexibility | ILCDR_1.2 DR Design | DLR/WD | Adjust baseline momentum compaction and explore options for adjustable momentum compaction

## Slide 11: DTC Lattice Characterization (WBS 1.2.1.2)
1 | 2 | 1 | 2 |  | DOE NC |  | 102-120 | DTC Lattice Characterization | ILCDR_1.2 DR Design | J. Crittenden | Characterize the Physics Performance for the TDR Baseline Lattice
1 | 2 | 1 | 2 | 1 | DOE NC |  | 102-121 | Dynamic Aperture | ILCDR_1.2 DR Design | DLR/JSh | DA improvement and evaluations for iterating the baseline DTC lattice
1 | 2 | 1 | 2 | 2 | DOE NC |  | 102-122 | Synchrotron Radiation Estimates | ILCDR_1.2 DR Design | K. Sonnad | Prepare synchrotron radiation distribution estimates for simulations using wall profiles developed as part of Task 1.2.2.3
1 | 2 | 1 | 2 | 3 | DOE NC |  | 102-123 | EC Build-Up Estimates | ILCDR_1.2 DR Design | JAC/MAF | Prepare EC build-up estimates for all DR operating modes
1 | 2 | 1 | 2 | 4 | DOE NC |  | 102-124 | EC Instability Estimates | ILCDR_1.2 DR Design | KS/MTFP | Prepare EC instability estimates for all DR operating modes
1 | 2 | 1 | 2 | 5 | DOE NC |  | 102-125 | Fill Pattern Requirements | ILCDR_1.2 DR Design | M. Palmer | Evaluate fill patter options for all DR operating modes
These items represent work where preparations are needed ASAP, but work will be steady for a number of months…
  1.2.1.2.1: Work needed as modifications implemented
  1.2.1.2.2: Needed ASAP but wall profile information (see next slides) is a pre-requisite
  1.2.1.2.3: EC build-up is major deliverable for later this fall
  1.2.1.2.4: EC instability estimates are major deliverable for later this fall
  1.2.1.2.5: All EC estimates must allow for 3 operational modes

## Slide 12: DTC Lattice Characterization (WBS 1.2.1.3)
These items represent ongoing interface issues. Effort will likely spike late this year through middle of next. Need points of contact immediately, however.
1 | 2 | 1 | 3 |  | DOE NC |  | 102-130 | Reporting | ILCDR_1.2 DR Design | M. Palmer | Coordinate Cornell Contributions to ILC GDE Report Structure for ILC TDP-II
1 | 2 | 1 | 3 | 1 | DOE NC |  | 102-131 | Lattice Design Contributions | ILCDR_1.2 DR Design | D. Rubin | Coordinate baseline lattice contributions to ILC reports
1 | 2 | 1 | 3 | 2 | DOE NC |  | 102-132 | Physics Results Contributions | ILCDR_1.2 DR Design | K. Sonnad | Coordinate physics simulations contributions to ILC reports
1 | 2 | 1 | 3 | 3 | DOE NC |  | 102-133 | EC Working Group Report Coordination | ILCDR_1.2 DR Design | J. Crittenden | Coordinate CU contributions to the EC Working Group Report
1 | 2 | 1 | 3 | 4 | DOE NC |  | 102-134 | Technical Design Contributions | ILCDR_1.2 DR Design | M. Billing | Coordinate technical system contributions to ILC reports
1 | 2 | 1 | 3 | 5 | DOE NC |  | 102-135 | ILC TDR Coordination | ILCDR_1.2 DR Design | M. Palmer | Coordinate ILC Technical Design Report effort

## Slide 13: Vacuum System Design (WBS 1.2.2.1)
More significant work than originally anticipated has landed in our laps…
  1.2.2.1.1: Targeting concepts before LCWS11
  1.2.2.1.2: Critical path for getting EC simulations underway
  1.2.2.1.3-5: Tasks to continue into early next year. Note that this is conceptual design level only!
1 | 2 | 2 | 1 |  | DOE NC |  | 102-210 | Vacuum System | ILCDR_1.2 DR Design | Y. Li | Incorporate EC Mitigations into ILC DR Vacuum Design and Participate in Overall System Design and Costing
1 | 2 | 2 | 1 | 1 | DOE NC |  | 102-211 | Cross-section Concept by Region | ILCDR_1.2 DR Design | YL/JVC | Develop vacuum chamber profiles consistent with EC mitigation recommendations (needed for overall conceptual design, EC simulations, and costing exercise)
1 | 2 | 2 | 1 | 2 | DOE NC |  | 102-212 | 3.2km Ring Wall Profile | ILCDR_1.2 DR Design | Y. Li | Prepare wall profile based on task 1.2.2.1.1 for use by EC simulation effort
1 | 2 | 2 | 1 | 3 | DOE NC |  | 102-213 | Vacuum Chamber Conceptual Designs Incorporating ECWG Mitigation Plan | ILCDR_1.2 DR Design | YL/JVC | Conceptual design of complete chambers incorporating EC mitigation recommendations
1 | 2 | 2 | 1 | 4 | DOE NC |  | 102-214 | Vacuum System Specifications | ILCDR_1.2 DR Design | Y. Li | Participate in overall vacuum system specification
1 | 2 | 2 | 1 | 5 | DOE NC |  | 102-215 | Vacuum System Cost Estimate | ILCDR_1.2 DR Design | YL/MAP | Participate in vacuum system costing exercise for the TDR

## Slide 14: Magnet System Design (WBS 1.2.2.2)
Significant amount of work in our hands between now and early next year (LCWS12 in late Feb-early March 2012, inputs to CFS by Jan 2012)
  Significant updates to RDR versions due to DTC parameters and new 10Hz operating mode
  Again, only conceptual design updates!
1 | 2 | 2 | 2 |  | DOE NC |  | 102-220 | Magnet System | ILCDR_1.2 DR Design | M. Palmer | Magnet System Design and Costing
1 | 2 | 2 | 2 | 1 | DOE NC |  | 102-221 | Re-scale magnet designs | ILCDR_1.2 DR Design | MAP/CS(SLAC) | Adjust conventional magnet specifications and designs for new baseline lattice
1 | 2 | 2 | 2 | 2 | DOE NC |  | 102-222 | Magnet cross-sections | ILCDR_1.2 DR Design | J. Conway | Provide updated magnet cross sections for ILC reference
1 | 2 | 2 | 2 | 3 | DOE NC |  | 102-223 | Re-scale power system | ILCDR_1.2 DR Design | MAP/PB(SLAC) | Update power supply system specifications for updated magnet specifications
1 | 2 | 2 | 2 | 4 | DOE NC |  | 102-224 | Short Period Wiggler Model | ILCDR_1.2 DR Design | J. Crittenden | Prepare short period wiggler model for characterization of the baseline lattice and for
1 | 2 | 2 | 2 | 5 | DOE NC |  | 102-225 | Wiggler Cryostat Specifications | ILCDR_1.2 DR Design | MAP/JVC | Update wiggler cryostat specifications for final magnet and vacuum chamber specifications
1 | 2 | 2 | 2 | 6 | DOE NC |  | 102-226 | Updated Wiggler Costing | ILCDR_1.2 DR Design | M. Palmer | Update costing for modified wiggler
1 | 2 | 2 | 2 | 7 | DOE NC |  | 102-227 | Multi-ring Magnet Stands Concept | ILCDR_1.2 DR Design | J. Conway | Update magnet stand conceptual design for new lattice and multi-ring layout
1 | 2 | 2 | 2 | 8 | DOE NC |  | 102-228 | Magnet Stands Costing | ILCDR_1.2 DR Design | J. Conway | Updated costing for modified stands
1 | 2 | 2 | 2 | 9 | DOE NC |  | 102-229 | Updated System Costing | ILCDR_1.2 DR Design | M. Palmer | Updated costing for full magnet and power supply system

## Slide 15: Instrumentation (WBS 1.2.2.3)
Modest amount of work anticipated here
  Key issue: RDR has no beam size monitor specified
  Generally just represents participation in overall review and confirmation that no major space requirements are left out of the layout.
1 | 2 | 2 | 3 |  | DOE NC |  | 102-230 | Instrumentation | ILCDR_1.2 DR Design | M. Billing | Instrumentation System Updates and Costing
1 | 2 | 2 | 3 | 1 | DOE NC |  | 102-231 | Instrumentation Requirements Review | ILCDR_1.2 DR Design | M. Billing | Review and update of DR instrumentation requirements
1 | 2 | 2 | 3 | 2 | DOE NC |  | 102-232 | Interface Issues (Magnets, Vacuum, CFS) | ILCDR_1.2 DR Design | MGB/JVC | Review of interface issues between instrumentation and other systems
1 | 2 | 2 | 3 | 3 | DOE NC |  | 102-233 | Instrumentation System Cost Review | ILCDR_1.2 DR Design | MGB/MAP | Cost review of instrumentation system

## Slide 16: Central Region Interface (WBS 1.2.2.4)
More significant work than originally anticipated is in this work package
  1.2.2.4.2: Targeting concepts before LCWS11
1 | 2 | 2 | 4 |  | DOE NC |  | 102-240 | ILC Central Region Interface | ILCDR_1.2 DR Design | M. Palmer | ILC Central Region Design and Interface
1 | 2 | 2 | 4 | 1 | DOE NC |  | 102-241 | CR Coordination | ILCDR_1.2 DR Design | M. Palmer | Coordinate interface of DR to injection and extraction systems
1 | 2 | 2 | 4 | 2 | DOE NC |  | 102-242 | Splitter/Merger Pulsed Element Specifications | ILCDR_1.2 DR Design | M. Billing | Provide specifications for the pulsed element system required for the high power upgrade with 2 positron damping rings
1 | 2 | 2 | 4 | 3 | DOE NC |  | 102-243 | Splitter/Merger Conceptual Design | ILCDR_1.2 DR Design | M. Billing | Provide a conceptual design for the splitter/merger pulsed elements and costing

## Slide 17: CF&S Interface (WBS 1.2.2.5)
Much work already in progress
Conventional Facilities and Siting group will need a major update by January 2012 so that their final design and costing exercise can be carried out.
1 | 2 | 2 | 5 |  | DOE NC |  | 102-250 | ILC CF&S Interface | ILCDR_1.2 DR Design | M. Palmer | Damping Ring Interface to the Conventional Facilities & Siting Group
1 | 2 | 2 | 5 | 1 | DOE NC |  | 102-251 | DTC Layout | ILCDR_1.2 DR Design | J. Conway | Layout specification for damping ring tunnel and support areas
1 | 2 | 2 | 5 | 2 | DOE NC |  | 102-252 | Inj/Ext Straight Layout | ILCDR_1.2 DR Design | J. Conway | Provide beam line layout information for tunnel layout
1 | 2 | 2 | 5 | 3 | DOE NC |  | 102-253 | Power Requirements | ILCDR_1.2 DR Design | M. Palmer | Provide updated power/cooling requirements for DR support infrastructure in the tunnel
1 | 2 | 2 | 5 | 4 | DOE NC |  | 102-254 | Equipment Layout | ILCDR_1.2 DR Design | MAP/JVC | Provide detailed information determining equipment layout tied to lattice for tunnel and alcove design

## Slide 18: Miscellaneous
Will prepare a Wiki page for this, and other, materials
Please don’t hesitate to come discuss individual tasks
I will be meeting with individuals where we need something to show at LCWS11